## Sheet1
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-05-28
Site |  | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178314 | 2022-01-11 | SS Railing | Cancell this requisition and raise the new requisition
178469 | 2022-03-29 | Coffee machine | On rental basis follow up with Vyshnavi enterprises
178470 | 2022-03-29 | Sofaset | Quotes to be receive from supplier
178471 | 2022-03-29 | Party speaker | PO 88728, Material deliverd
178472 | 2022-03-29 | Paper dispenser | PO 88336
178544 | 2022-05-04 | Vinyl flooring | Under rates negotiation with procurment team
178556 | 2022-05-12 | MI Cameras | PO 88760
178565 | 2022-05-24 | MI Cameras | PO 88761
178566 | 2022-05-24 | Main door light | PO to be issue
178568 | 2022-05-25 | Kitchen unit | Drawings to be receive
178569 | 2022-05-25 | Tarpaulin cover | Requisition sent to MDs approval
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177487 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order material is under delivery as per site requirment
177488 | 18.03.2021 | MCBs,modular plate ,socket | Bulk order material is under delivery as per site requirment
177498 | 19.03.2021 | Stainless steel sink | Bulk order 12 balance from supplier will be deliverd by next week
178122 | 26.10.2021 | UPVC Windows | PO 82206 is deliverd, PO 82144 is work under process
178125 | 29.10.2021 | Wall mixtures | Bulk order material is under delivery as per site requirment
178126 | 29.10.2021 | Wall mixtures | Bulk order material is under delivery as per site requirment
178127 | 29.10.2021 | Wall hung WC | Bulk order material is under delivery as per site requirment
178128 | 29.10.2021 | Wall hung WC | Bulk order material is under delivery as per site requirment
178191 | 23.11.2021 | Glass partition | Deliverd
178208 | 30.11.2021 | UPVC Windows | PO 83446 is deliverd completed, PO 83444 work is under process
178302 | 07.01.2022 | UPVC windows | Deliverd
178304 | 07.01.2022 | UPVC windows | Work under progress, ARN upvc
178311 | 11.01.2022 | UPVC sliding windows | Work under progress
178312 | 11.01.2022 | Glass partition | Deliverd
178317 | 12.01.2022 | UPVC sliding windows | Work under progress
178361 | 02.02.2022 | UPVC windows | Deliverd
178397 | 2022-02-21 | Sliding windows | Work under progress, sudarshan
178428 | 14.03.2022 | Plywood | Pick up from Sri sai rohit marketing
178440 | 2022-03-21 | Grills | Deliverd
178452 | 2022-03-25 | Sliding windows | Work under process
178455 | 2022-03-26 | Creche equipments | Deliverd
178456 | 2022-03-26 | Creche equipments | Deliverd
178465 | 2022-03-29 | Notice board | Work under process by raja chary
178467 | 2022-03-29 | Recreation room material | Deliverd
178468 | 2022-03-29 | Playground material | Material is under fabrication
178447 | 2022-03-31 | Toughned glass | Deliverd
178478 | 2022-04-05 | Sliding windows | Part deliverd, balance work under process
178479 | 2022-04-05 | Grills | Deliverd
178480 | 2022-04-05 | Sliding windows | Work under process
178481 | 2022-04-05 | Grills | Part material deliverd, balance work under process
178510 | 2022-04-16 | HOB and Chimney | Next week delivery
178512 | 2022-04-16 | Glass partition | Work under process
178514 | 2022-04-18 | Kitchen unit | Work under process
178518 | 2022-04-23 | Name plate club house | Work under process
178522 | 2022-04-23 | Wood dark | Pick up from SSLLP-GMR
178529 | 2022-04-28 | Roots clean machine | Next month first week delivery
178535 | 2022-04-30 | Name plate. | Work under process
178536 | 2022-05-02 | Rain water filteration plant | Work under process
178537 | 2022-05-02 | Sewage filtration plant | Work under process
178545 | 2022-05-05 | French windows | Work under process
178547 | 2022-05-06 | Wood dark tiles | Pick up from SSLLP-GMR
178552 | 2022-05-09 | Lappum patti | Deliverd
178551 | 2022-05-09 | Tiles | Pick up from SSLLP-GMR