## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-05-28
Site |  | GVRC
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
163820 | 2022-04-07 | Welded mesh | Cancelled due to incorrect specifications
164824 | 2022-04-09 | GI Cable tray | Cancelled another po issued remove from this list
164835 | 2022-04-12 | Safety material | PO 87539,87540
164836 | 2022-04-12 | Aluminium cladding | Missing requisition po to be issue
164858 | 2022-04-16 | Letten mirror | No stock in IKEA
164862 | 2022-04-16 | GI Flat patti | Missing requisition po to be issue
164880 | 2022-04-20 | Toughned glass | Estimate to be prepare
164888 | 2022-04-23 | Lithiaum battary | Local purchase by site
164898 | 2022-04-24 | Black bitumen tape | PO 87790
164915 | 2022-05-04 | Lightning arrestor | Estimate to be prepare
164941 | 2022-05-10 | Persnol computer | Note with MD by suneel
164956 | 2022-05-16 | Toughned glass | Estimate to be prepare
164963 | 2022-05-17 | SD Cards | Cancelled by suneel
164958 | 2022-05-16 | 4'' led pannel light 2 way a switch | Estimate to be prepare
164959 | 2022-05-16 | Surface mounted tube light | PO 88423
164960 | 2022-05-16 | Gusset panel | PO 88349
164965 | 2022-05-19 | B Class pipe, flat patti | Estimate to be prepare
164969 | 2022-05-19 | GU U clamp, nuts and washers | Requisition not found send again
164977 | 2022-05-24 | Wardrobe | PO 88539
164978 | 2022-05-25 | 3 Core flexible copper cable, top in plug | PO to be issue
164979 | 2022-05-25 | 50 watts flood lights, umbrella stand for side flood light
List of requisitions Where PO/WO is prepared and items have not received at site
163704 | 2021-08-07 | ACP cladding | Work under progress
164815 | 2022-04-07 | Flame proof lights | Update will bereceiving from supplier on ststus of material
164829 | 2022-04-09 | Cera board | Work under process by karunakar,clarification required from madhu to karunakar
164834 | 2022-04-11 | Vaccum deassaer cover | Under fabrication with supplier
164851 | 2022-04-14 | Bathroom door | No response from supplier will get back to you once we speak to supplier
164866 | 2022-04-16 | Vision clip and hole plugs | Send driver to collect material with PO, meet MR. Nandu
164879 | 2022-04-20 | Panel doors | Delivered by Sri Sai Decors on 23-5-22
164891 | 2022-04-23 | Aerocon panels | PO with MD sir for approval
164894 | 2022-04-23 | FRD Doors | Supplier will confirm the delivery date
164897 | 2022-04-25 | ETP/STP Material | Next week delivery
164913 | 2022-04-30 | Asian ace | Pick up from Ganji venkanna and sons
164916 | 2022-05-05 | Toughned glass with patch | False ceiling work is not completed after completed then only he will proceed supplier spoken to Mr. Bhagat
164918 | 2022-05-05 | Toughned glass with patch | False ceiling work is not completed after completed then only he will proceed supplier spoken to Mr. Bhagat
164920 | 2022-05-06 | PU Foam | Pick up from Supplier place
164923 | 2022-05-05 | Luminious inverter battary | Next week delivery
164928 | 2022-05-05 | CCTV Bullet camera | Payment is under process
164929 | 2022-05-06 | ACP cladding | Work under process Pinnaccle
164923 | 2022-05-11 | ACP Walls pop work | Work under process
164944 | 2022-05-11 | Surface lights | Pick up from Reflections electricals
164947 | 2022-05-12 | Starter | Pick up from PEC
164962 | 2022-05-17 | Indigo exterior paints | Pick up from Veesam shetty
164964 | 2022-05-17 | Blue sheets | Pick up from SSLLP stock in hand
164974 | 2022-05-23 | Wheel barrow | Advance payment is under process Po issued to Industrail equipments.
164976 | 2022-05-24 | Fire alaram gong valve | Delivered on 30-5-22
164980 | 2022-05-25 | Dol starter, cutter pump | Pick up material from Andhra Pumps, the material is ready with supplier