## Vista
Prepared by: | vanajakshi
Report Date | 31.05.2022
Site | Serene Farms
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
150629 | 11.04.2022 | submersible motor | Estimation sent to MD'S approval
List of requisitions Where PO/WO is prepared and items have not received at site
150638 | 12.05.2022 | Big torch lights | Stock available at SSLLP.Deliver by next week,waiting for vehicle arrangement
150638 | 12.05.2022 | Torch lights | Stock available at SSLLP.Deliver by next week,waiting for vehicle arrangement
150638 | 12.05.2022 | Camera charger | Deliver by next week