## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-06-04
Site |  | GVRC
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
164835 | 2022-04-12 | Safety material | PO 87539,87540
164858 | 2022-04-16 | Letten mirror | PO 89144
164880 | 2022-04-20 | Toughned glass | Estimate to be prepare
164915 | 2022-05-04 | Lightning arrestor | PO 88859,89053
164941 | 2022-05-10 | Persnol computer | Note with MD by suneel
164956 | 2022-05-16 | Toughned glass | PO 88887
164969 | 2022-05-19 | GI U clamp, nuts and washers | PO 89142
164978 | 2022-05-25 | 3 Core flexible copper cable, top in plug | PO 88787
164984 | 2022-06-02 | Main door frames | PO 88950
164986 | 2022-05-26 | MS Plates with 2 holes | Local purchase and deliverd to site 40 nos
164987 | 2022-05-17 | Galvalume sheet | Po to be issue
164988 | 2022-05-27 | Loto lock | One sample has been ordered once the sample approved will ordered balance
164993 | 2022-05-30 | JBL CSL M 20 | Online purchase
164995 | 2022-05-30 | Plexi glass | PO 89071
164997 | 2022-05-01 | Square rod | PO 88904
List of requisitions Where PO/WO is prepared and items have not received at site
163704 | 2021-08-07 | ACP cladding | Work under progress
164815 | 2022-04-07 | Flame proof lights | Deliverd
164829 | 2022-04-09 | Cera board | Work under process by karunakar,clarification required from madhu to karunakar
164851 | 2022-04-14 | Bathroom door | No response from supplier will get back to you once we speak to supplier
164891 | 2022-04-23 | Aerocon panels | PO with MD sir for approval
164894 | 2022-04-23 | FRD Doors | Supplier will confirm the delivery date
164897 | 2022-04-25 | ETP/STP Material | Deliverd
164916 | 2022-05-05 | Toughned glass with patch | False ceiling work is not completed after completed then only he will proceed supplier spoken to Mr. Bhagat
164918 | 2022-05-05 | Toughned glass with patch | False ceiling work is not completed after completed then only he will proceed supplier spoken to Mr. Bhagat
164920 | 2022-05-06 | PU Foam | Pick up from Supplier place
164923 | 2022-05-05 | Luminious inverter battary | Next week delivery
164928 | 2022-05-05 | CCTV Bullet camera | Deliverd
164929 | 2022-05-06 | ACP cladding | Work under process Pinnaccle
164923 | 2022-05-11 | ACP Walls pop work | Work under process
164965 | 2022-05-19 | B calss pipe , flat patti | Pick up from Supplier place
164977 | 2022-05-24 | Wardrobe | Next week delivery
164982 | 2022-05-25 | Flush door | Tomorrow delivery
164989 | 2022-05-27 | Auto glow radio, acp sheet | Deliverd
164974 | 2022-05-23 | Wheel barrow | Advance payment is under process Po issued to Industrail equipments.
164994 | 2022-05-30 | MS Street light pole | Pick up from Supplier place