## NE
Prepared by: | Mounika
Report Date | 11.06.22
Site | Nilgiri Estates
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
175325 | 20.07.21 | Solar Module | Legal case in MD going with this supplier
175492 | 07.03.22 | Sliding Windows | This week delivary
175503 | 08.04.22 | Mosquito Mesh | Supplier will arrange