## VOC LLP
Prepared by: | Mounika
Report Date | 18.06.22
Site | Nxetopolis
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
186330 | 06.06.22 | MS Stool | Monday delivered
186312 | 14.05.22 | Nylon Cricket net | This week delivary
186328 | 30.05.22 | JBL | Delivired
186260 | 29.03.22 | Biometric Battry | Cancelled
186331 | 06.06.22 | FRP Thadkas | Tuesday Delivary