## A-Block
Company Name Modiproperties.Pvt Ltd
Project |  | GULMOHAR RESDIENCY
Prepared By |  | Ramprasad M
Last updated on |  | 28-06-22
Block No |  | Block - A
S.No | Flat No | Plinth beam casting Date | Slab casting date | Stage - I BW & internal plastering completion date | Stage II Completion date (Fooring, Bathroom Tiles, 1st Coat Painting) | Stage III completion date | Remarks
1 | A - 101 | NA | 24-07-20 | 23-09-20 | 02-11-20 | 17-11-20 | Model flat
2 | A - 102 | 27-12-19 | 24-07-20 | 26-12-20 | 03-05-21 | 20-10-21
3 | A - 103 | 27-12-19 | 2020-11-07 | 14-12-20 | 01-06-21 | 20-10-21
4 | A - 104 | 27-12-19 | 2020-11-07 | 19-12-20 | 03-05-21 | 20-10-21
5 | A - 105 | 17-12-19 | 2020-11-07 | 14-12-20 | 03-05-21 | 01-11-21
6 | A - 106 | 27-12-19 | 2020-11-07 | 19-12-20 | 07-06-21 | 01-11-21
7 | A - 107 | 06-01-20 | 2020-11-07 | 14-12-20 | 07-06-21 | 01-11-21
8 | A - 108 | 18-01-20 | 24-07-20 | 19-12-20 | 01-06-21 | 20-10-21
9 | A - 109 | N/A | 24-07-20 | 22-09-20 | 02-11-20 | 17-11-20
10 | A - 201 | N/A | 20-10-20 | 31-01-21 |  |  | unsold
11 | A - 202 |  | 20-10-20 | 06-03-21 |  |  | unsold
12 | A - 203 |  | 10-10-20 | 06-03-21 | 2022-11-01 | 25-02-22 | Model flat
13 | A - 204 |  | 10-10-20 | 31-01-21 |  |  | unsold
14 | A - 205 |  | 10-10-20 | 28-12-20 | 03-05-21 | 01-11-21
15 | A - 206 |  | 10-10-20 | 14-01-21 |  |  | unsold
16 | A - 207 |  | 10-10-20 | 06-03-21 | 2022-11-01 | 25-02-22 | Model flat
17 | A - 208 |  | 20-10-20 | 06-03-21 |  |  | unsold
18 | A - 209 | N/A | 20-10-20 | 06-03-21 | 14-06-21 | 14-02-22
19 | A - 301 | N/A | 05-12-20 | 27-03-21 | 25-08-21 | 01-11-21
20 | A - 302 |  | 05-12-20 | 27-03-21 | 03-05-21 | 06-11-21
21 | A - 303 |  | 24-11-20 | 11-03-21 | 31-08-21 | 09-01-22
22 | A - 304 |  | 24-11-20 | 11-03-21 | 14-06-21 | 06-11-21
23 | A - 305 |  | 24-11-20 | 15-03-21 | 19-07-21 | 01-11-21
24 | A - 306 |  | 24-11-20 | 06-03-21 | 15-09-21 | 25-02-22
25 | A - 307 |  | 24-11-20 | 11-03-21 | 14-06-21 | 10-01-22
26 | A - 308 |  | 05-12-20 | 11-03-21 | 03-05-21 | 10-01-22
27 | A - 309 | N/A | 05-12-20 | 27-03-21 | 06-10-21 | 14-02-22
28 | A- 401 | N/A | 31-12-20 | 03-05-21 | 25-08-21 | 14-02-22
29 | A- 402 |  | 31-12-20 | 26-04-21 | 17-08-21 | 25-02-22
30 | A- 403 |  | 31-12-20 | 26-04-21 | 28-06-21 | 10-01-22
31 | A- 404 |  | 31-12-20 | 26-04-21 | 21-09-21 | 09-01-22
32 | A- 405 |  | 31-12-20 | 26-04-21 | 15-09-21 | 14-02-22
33 | A- 406 |  | 31-12-20 | 10-05-21 | 31-08-21 | 25-02-22
34 | A- 407 |  | 31-12-20 | 26-04-21 | 21-09-21 | 10-01-22
35 | A- 408 |  | 31-12-20 | 26-04-21 | 25-08-21 | 14-02-22
36 | A- 409 | N/A | 31-12-20 | 03-05-21 | 25-08-21 | 25-02-22
37 | A - 501 | N/A | 21-02-21 | 23-06-21 | 20-10-21 | 12-01-22
38 | A - 502 |  | 21-02-21 | 08-06-21 | 11-11-21 | 12-01-22
39 | A - 503 |  | 21-02-21 | 08-06-21 | 28-11-21 | 14-02-22
40 | A - 504 |  | 21-02-21 | 23-06-21 | 20-10-21 | 05.02.22
41 | A - 505 |  | 21-02-21 | 23-06-21 | 01-11-21 | 14-02-22
42 | A - 506 |  | 21-02-21 | 23-06-21 | 28-11-21 | 25-02-22
43 | A - 507 |  | 21-02-21 | 08-06-21 | 01-11-21 | 25-02-22
44 | A - 508 |  | 21-02-21 | 28-06-21 | 28-11-21 | 25-02-22
45 | A - 509 | N/A | 21-02-21 | 28-06-21 | 16-12-21 | 25-02-22

## B-Block
Company Name Modiproperties.Pvt Ltd
Project |  | GULMOHAR RESDIENCY
Prepared By |  | Ramprasad
Last updated on |  | 28-06-22
Block No |  | Block -B
S.No | Flat No | Plinth beam casting Date | Slab casting date | Stage - I BW & internal plastering completion date | Stage II Completion date (Fooring, Bathroom Tiles, 1st Coat Painting) | Stage III completion date | Remarks
1 | B- 101 | N \ A | 18-03-2020 | 19-12-20 | 15-09-21 |  | Balcony railing balance
2 | B- 102 | N \ A | 08-03-2020 | 26-12-20 | 15-09-21 |  | Balcony railing balance
3 | B- 103 | N \ A | 08-03-2020 | 19-12-20 | 15-09-21 | 18-05-22 | Balcony railing balance
4 | B- 104 | N \ A | 08-03-2020 | 20-08-20 | 02-11-20 | 17-11-20 | Model flat
5 | B- 105 | N \ A | 08-03-2020 | 20-08-20 | 02-11-20 | 17-11-20 | Model flat
6 | B- 106 | N \ A | 08-03-2020 | 15-10-20 |  |  | Previously Site office
7 | B- 107 | N \ A | 08-03-2020 | 19-12-20 | 01-11-21 | 01.04.222 | upvc window 1
8 | B- 108 | N \ A | 18-03-2020 | 19-12-20 | 15-09-21 | 18-05-22
9 | B- 201 | N \ A | 19-09-2020 | 29-12-20 |  |  | unsold
10 | B- 202 | N \ A | 19-09-2020 | 15-01-21 |  |  | unsold
11 | B- 203 | N \ A | 23-06-2020 | 15-01-21 |  |  | unsold
12 | B- 204 | N \ A | 23-06-2020 | 15-01-21 | 15-09-21 | 28-02-22
13 | B- 205 | N \ A | 23-06-2020 | 15-01-21 | 15-09-21 | 28-02-22
14 | B- 206 | N \ A | 23-06-2020 | 29-12-20 |  |  | unsold
15 | B- 207 | N \ A | 19-09-2020 | 19-12-20 |  |  | unsold
16 | B- 208 | N \ A | 19-09-2020 | 19-12-20 |  |  | unsold
17 | B - 301 | N \ A | 20-10-2020 | 02-03-21 | 28.03.22 | 02.04.2022
18 | B - 302 | N \ A | 20-10-2020 | 02-03-21 | 2022-12-01 | 28-02-22
19 | B - 303 | N \ A | 28-09-2020 | 02-03-21 | 06-11-21 | 25-03-22
20 | B - 304 | N \ A | 28-09-2020 | 02-03-21 | 15-09-21 | 01.04.2022
21 | B - 305 | N \ A | 28-09-2020 | 24-03-21 | 15-09-21 | 28-02-22
22 | B - 306 | N \ A | 28-09-2020 | 31-01-21 |  |  | false celing work in progress
23 | B - 307 | N \ A | 20-10-2020 | 02-03-21 | 24-12-21 | 02.04.2022
24 | B - 308 | N \ A | 20-10-2020 | 31-01-21 | 15-09-21 | 03.04.2022
25 | B - 401 | N \ A | 13-11-2020 | 12-03-21 | 04-01-22 | 18.04.2022
26 | B - 402 | N \ A | 13-11-2020 | 27-03-21 | 15-09-21 | 25-03-22
27 | B - 403 | N \ A | 24-10-2020 | 27-03-21 | 13-01-22 | 05.04.2022
28 | B - 404 | N \ A | 24-10-2020 | 02-03-21 | 01-11-21 | 25-03-22
29 | B - 405 | N \ A | 24-10-2020 | 02-03-21 | 15-09-21 | 25-03-22
30 | B - 406 | N \ A | 24-10-2020 | 24-03-21 | 13-01-22 | 10.04.2022
31 | B - 407 | N \ A | 13-11-2020 | 12-03-21 | 13-01-22 | 10.04.2022
32 | B - 408 | N \ A | 13-11-2020 | 02-03-21 | 15-09-21 | 10.04.2022
33 | B - 501 | N \ A | 2020-12-12 | 26-04-21 | 25-02-22 | 18.04.2022
34 | B - 502 | N \ A | 2020-12-12 | 30-04-21 | 04-01-22 | 25-03-22
35 | B - 503 | N \ A | 20-11-2020 | 30-04-21 | 25-02-22 | 25-03-22
36 | B - 504 | N \ A | 20-11-2020 | 26-04-21 | 24-12-21 | 25-03-22
37 | B - 505 | N \ A | 20-11-2020 | 28-06-21 | 24-12-21 | 19.04.2022
38 | B - 506 | N \ A | 20-11-2020 | 28-06-21 | 25-02-22 | 19.04.2022
39 | B - 507 | N \ A | 2020-12-12 | 30-04-21 | 13-01-22 | 15.04.2022
40 | B - 508 | N \ A | 2020-12-12 | 26-04-21 | 24-12-21 | 01.04.2022
41 | B - 601 | N \ A | 29-06-21 | 01-11-21 | 25-02-22 |  | tiles work
42 | B - 602 | N \ A | 29-06-21 | 20-10-21 |  |  | Flooring work in progress
43 | B - 603 | N \ A | 26-05-21 | 20-10-21 | 01.04.2022 | 18.04.2022
44 | B - 604 | N \ A | 26-05-21 | 20-10-21 | 25-02-22 | 18-05-22 | balcony glass
45 | B - 605 | N \ A | 26-05-21 | 20-10-21 | 25-02-22 |  | ready for qc
46 | B - 606 | N \ A | 26-05-21 | 20-10-21 |  |  | unsold
47 | B - 607 | N \ A | 29-06-21 | 20-10-21 |  |  | unsold
48 | B - 608 | N \ A | 29-06-21 | 20-10-21 | 25-02-22 | 18-05-22 | balcony glass

## C-Block
Company Name Modiproperties.Pvt Ltd
Project |  | GULMOHAR RESDIENCY
Prepared By
Last updated on |  | 28-06-22
Block No |  | Block - C
S.No | Flat No | Plinth beam casting Date | Slab casting date | Stage - I BW & internal plastering completion date | Stage II Completion date (Fooring, Bathroom Tiles, 1st Coat Painting) | Stage III completion date | Remarks
1 | C - 101 | 12-03-21 | 13-09-21 | 30-11-21 |  |  | Stage-2 works in progress
2 | C - 102 | 12-03-21 | 13-09-21 | 30-11-21 |  |  | Stage-2 works in progress
3 | C - 103 | 12-03-21 | 08-09-21 | 30-11-21 |  |  | Stage-2 works in progress
4 | C - 104 | 12-03-21 | 08-09-21 | 30-11-21 |  |  | Stage-2 works in progress
5 | C - 105 | 12-03-21 | 08-09-21 | 30-11-21 |  |  | Stage-2 works in progress
6 | C - 106 | 12-03-21 | 13-09-21 | 30-11-21 |  |  | Stage-2 works in progress
7 | C - 107 | 12-03-21 | 13-09-21 | 30-11-21 |  |  | Stage-2 works in progress
8 | C - 201 | 12-03-21 | 20-10-21 | 04-01-22
9 | C - 202 | 12-03-21 | 20-10-21 | 04-01-22
10 | C - 203 | 12-03-21 | 10-10-21 | 04-01-22
11 | C - 204 | 12-03-21 | 10-10-21 | 04-01-22 |  |  | Stage-2 works in progress
12 | C - 205 | 12-03-21 | 20-10-21 | 04-01-22
13 | C - 206 | 12-03-21 | 20-10-21 | 04-01-22
14 | C - 207 | 12-03-21 | 20-10-21 | 04-01-22 |  |  | Stage-2 works in progress
15 | C - 301 | 12-03-21 | 26-11-21 | 26-02-22 |  |  | Stage-2 works in progress
16 | C - 302 | 12-03-21 | 26-11-21 | 26-02-22
17 | C - 303 | 12-03-21 | 26-11-21 | 26-02-22
18 | C - 304 | 12-03-21 | 26-11-21 | 26-02-22 |  |  | Stage-2 works in progress
19 | C - 305 | 12-03-21 | 26-11-21 | 26-02-22 |  |  | Stage-2 works in progress
20 | C - 306 | 12-03-21 | 26-11-21 | 26-02-22 |  |  | Stage-2 works in progress
21 | C - 307 | 12-03-21 | 26-11-21 | 26-02-22 |  |  | Stage-2 works in progress
22 | C - 401 | 12-03-21 | 22-01-07 | 14-03-22
23 | C - 402 | 12-03-21 | 22-01-07 | 14-03-22
24 | C - 403 | 12-03-21 | 21-12-21 | 14-03-22
25 | C - 404 | 12-03-21 | 21-12-21 | 14-03-22
26 | C - 405 | 12-03-21 | 21-12-21 | 14-03-22
27 | C - 406 | 12-03-21 | 22-01-07 | 14-03-22
28 | C - 407 | 12-03-21 | 22-01-07 | 14-03-22
29 | C - 501 | 12-03-21 | 10-02-22 | 28-04-22 |  |  | Stage-1 works in progress
30 | C - 502 | 12-03-21 | 10-02-22 | 28-04-22 |  |  | Stage-1 works in progress
31 | C - 503 | 12-03-21 | 10-02-22 | 14-03-22 |  |  | Stage-1 works in progress
32 | C - 504 | 12-03-21 | 10-02-22 | 14-03-22 |  |  | Stage-1 works in progress
33 | C - 505 | 12-03-21 | 10-02-22 | 28-04-22 |  |  | Stage-1 works in progress
34 | C - 506 | 12-03-21 | 10-02-22 | 28-04-22 |  |  | Stage-1 works in progress
35 | C - 507 | 12-03-21 | 10-02-22 | 16-04-22 |  |  | Stage-1 works in progress
36 | C - 601 | 12-03-21 | 08-06-22 |  |  |  | Brick Work in progress
37 | C - 602 | 12-03-21 | 15-04-22 |  |  |  | Brick Work in progress
38 | C - 603 | 12-03-21 | 03-03-22 | 15-06-22 |  |  | Brick Work in progress
39 | C - 604 | 12-03-21 | 03-03-22 | 15-06-22 |  |  | plastering in progress
40 | C - 605 | 12-03-21 | 03-03-22 | 15-06-22 |  |  | plastering in progress
41 | C - 606 | 12-03-21 | 15-04-22 |  |  |  | plastering in progress
42 | C - 607 | 12-03-21 | 08-06-22 |  |  |  | Brick Work in progress

## D- Block
Company Name Modiproperties.Pvt Ltd
Project |  | GULMOHAR RESDIENCY
Prepared By
Last updated on |  | 28-06-22
Block No |  | Block - D
S.No | Flat No | Plinth beam casting Date | Slab casting date | Stage - I BW & internal plastering completion date | Stage II Completion date (Fooring, Bathroom Tiles, 1st Coat Painting) | Stage III completion date | Remarks
1 | D - 101 | 08-06-21 | 28-07-21 |  |  |  | plumbing/elect progress
2 | D - 102 | 08-06-21 | 28-07-21 | 14-02-22 |  |  | unsold
3 | D - 103 | 12-03-21 | 25-07-21 | 04-01-22 |  |  | unsold
4 | D - 104 | 12-03-21 | 25-07-21 | 04-01-22 |  |  | unsold
5 | D - 105 | 12-03-21 | 25-07-21 | 04-01-22 | 2022-02-06
6 | D - 106 | 12-03-21 | 25-07-21 | 04-01-22 | 2022-02-06
7 | D - 107 | 08-06-21 | 28-07-21 | 14-02-22 |  |  | unsold
8 | D - 108 | 08-06-21 | 28-07-21 | 14-02-22 | 2022-02-06
9 | D - 201 | 08-06-21 | 18-08-21 | 14-02-22 |  |  | unsold
10 | D - 202 | 08-06-21 | 18-08-21 | 14-02-22 |  |  | unsold
11 | D - 203 | 12-03-21 | 18-08-21 | 14-02-22 |  |  | unsold
12 | D - 204 | 12-03-21 | 18-08-21 | 14-02-22 |  |  | unsold
13 | D - 205 | 12-03-21 | 18-08-21 | 14-02-22 |  |  | Customer to provide tiles
14 | D - 206 | 12-03-21 | 18-08-21 | 14-02-22 |  |  | unsold
15 | D - 207 | 08-06-21 | 18-08-21 | 14-02-22 |  |  | unsold
16 | D - 208 | 08-06-21 | 18-08-21 | 14-02-22 |  |  | painting work in progress
17 | D - 301 | 08-06-21 | 08-09-21 | 14-03-22 |  |  | Putty work by Customer
18 | D - 302 | 08-06-21 | 08-09-21 | 14-03-22 |  |  | painting work in progress
19 | D - 303 | 12-03-21 | 08-09-21 | 14-03-22 |  |  | painting work under progress
20 | D - 304 | 12-03-21 | 08-09-21 | 14-03-22 |  |  | Customer to provide tiles
21 | D - 305 | 12-03-21 | 08-09-21 | 14-03-22 |  |  | Flooring work under progress
22 | D - 306 | 12-03-21 | 08-09-21 | 14-03-22
23 | D - 307 | 08-06-21 | 08-09-21 | 14-03-22
24 | D - 308 | 08-06-21 | 08-09-21 | 14-03-22 |  |  | Flooring work under progress
25 | D - 401 | 08-06-21 | 27-09-21 | 18-05-22
26 | D - 402 | 08-06-21 | 27-09-21 | 18-05-22
27 | D - 403 | 12-03-21 | 27-09-21 | 18-05-22
28 | D - 404 | 12-03-21 | 27-09-21 | 18-05-22
29 | D - 405 | 12-03-21 | 27-09-21 | 18-05-22 |  |  | Putty work by Customer
30 | D - 406 | 12-03-21 | 27-09-21 | 18-05-22 |  |  | Putty work by Customer
31 | D - 407 | 08-06-21 | 27-09-21 | 18-05-22
32 | D - 408 | 08-06-21 | 27-09-21 | 18-05-22
33 | D - 501 | 08-06-21 | 20-10-21 | 01-06-22
34 | D - 502 | 08-06-21 | 20-10-21 | 05-06-22
35 | D - 503 | 12-03-21 | 20-10-21 | 05-06-22
36 | D - 504 | 12-03-21 | 20-10-21 | 05-06-22
37 | D - 505 | 12-03-21 | 20-10-21 | 05-06-22
38 | D - 506 | 12-03-21 | 20-10-21 | 05-06-22
39 | D - 507 | 08-06-21 | 20-10-21 | 01-06-22
40 | D - 508 | 08-06-21 | 20-10-21 | 01-06-22
41 | D - 601 | 08-06-21 | 14-11-21 |  |  |  | plastering in progress
42 | D - 602 | 08-06-21 | 14-11-21 |  |  |  | plastering in progress
43 | D - 603 | 12-03-21 | 14-11-21 |  |  |  | plastering in progress
44 | D - 604 | 12-03-21 | 14-11-21 |  |  |  | plastering in progress
45 | D - 605 | 12-03-21 | 14-11-21 |  |  |  | plastering in progress
46 | D - 606 | 12-03-21 | 14-11-21 |  |  |  | plastering in progress
47 | D - 607 | 08-06-21 | 14-11-21 |  |  |  | plastering in progress
48 | D - 608 | 08-06-21 | 14-11-21 |  |  |  | plastering in progress

## E-Block
Company Name Modiproperties.Pvt Ltd
Project |  | GULMOHAR RESDIENCY
Prepared By
Last updated on
Block No |  | Block - E
S.No | Flat No | Plinth beam casting Date | Slab casting date | Stage - I BW & internal plastering completion date | Stage II Completion date (Fooring, Bathroom Tiles, 1st Coat Painting) | Stage III completion date | Remarks
1 | E - 101
2 | E - 102
3 | E - 103
4 | E - 104
5 | E - 105
6 | E - 106
7 | E - 107
8 | E - 201
9 | E - 202
10 | E - 203
11 | E - 204
12 | E - 205
13 | E - 206
14 | E - 207
15 | E - 301
16 | E - 302
17 | E - 303
18 | E - 304
19 | E - 305
20 | E - 306
21 | E - 307
22 | E - 401
23 | E - 402
24 | E - 403
25 | E - 404
26 | E - 405
27 | E - 406
28 | E - 407
29 | E- 501
30 | E- 502
31 | E- 503
32 | E- 504
33 | E- 505
34 | E- 506
35 | E- 507
36 | E- 601
37 | E- 602
38 | E- 603
39 | E- 604
40 | E- 605
41 | E- 606
42 | E- 607

## F- Block
Company Name Modiproperties.Pvt Ltd
Project |  | GULMOHAR RESDIENCY
Prepared By
Last updated on |  | 28-06-22
Block No |  | Block - F
S.No | Flat No | Plinth beam casting Date | Slab casting date | Stage - I BW & internal plastering completion date | Stage II Completion date (Fooring, Bathroom Tiles, 1st Coat Painting) | Stage III completion date | Remarks
1 | F - 101 | 14-11-20 | 12-12-20 | 30-04-21 | 2022-11-01 |  | Stage 3 progress
2 | F - 102 | 14-01-21 | 08-02-21 | 16-08-21 | 22-03-22 |  | Stage 3 progress
3 | F - 103 | 31-05-21 | 01-08-21 | 04-01-22 | 15-06-22 |  | Stage 3 progress
4 | F - 104 | 26-05-21 | 01-08-21 | 04-01-22 | 15-06-22 |  | Stage 3 progress
5 | F - 105 | 14-01-21 | 08-02-21 | 03-08-21 |  |  | unsold
6 | F - 106 | 14-11-20 | 12-12-20 | 30-04-21 | 2022-11-01 |  | Stage 3 progress
7 | F - 201 | 14-11-20 | 30-12-20 | 08-06-21 |  |  | mortigage flat
8 | F - 202 | 14-01-21 | 19-03-21 | 05-10-21 |  |  | mortigage flat
9 | F - 203 | 31-05-21 | 03-09-21 | 14-02-22 |  |  | mortigage flat
10 | F - 204 | 26-05-21 | 03-09-21 | 14-02-22 |  |  | mortigage flat
11 | F - 205 | 14-01-21 | 19-03-21 | 08-09-21 |  |  | mortigage flat
12 | F - 206 | 14-11-20 | 30-12-20 | 08-06-21 |  |  | mortigage flat
13 | F - 301 | 14-11-20 | 10-02-21 | 14-06-21 | 14-03-22 |  | switches fixing
14 | F - 302 | 14-01-21 | 23-06-21 | 28-11-21 |  |  | granite work
15 | F - 303 | 31-05-21 | 16-09-21 | 28-02-22 |  |  | tiles work
16 | F - 304 | 26-05-21 | 16-09-21 | 14-03-22 |  |  | painting work
17 | F - 305 | 14-01-21 | 23-06-21 | 28-11-21 |  |  | painting work
18 | F - 306 | 14-11-20 | 10-02-21 | 14-06-21 | 14-03-22 |  | switches fixing
19 | F - 401 | 14-11-20 | 06-03-21 | 25-08-21 | 14-03-22
20 | F - 402 | 14-01-21 | 30-08-21 | 25-03-22 |  |  | tiles work
21 | F - 403 | 31-05-21 | 26-10-21 | 14-02-22 |  |  | tiles work
22 | F - 404 | 26-05-21 | 26-10-21 | 14-02-22 |  |  | painting work
23 | F - 405 | 14-01-21 | 30-08-21 | 28-02-22 |  |  | tiles work
24 | F - 406 | 14-11-20 | 06-03-21 | 25-08-21 | 14-03-22
25 | F - 501 | 14-11-20 | 19-03-21 | 14-02-22 | 15-06-22
26 | F - 502 | 14-01-21 | 16-09-21 | 25-03-22 |  |  | tiles work
27 | F - 503 | 31-05-21 | 02-11-21 | 25-03-22 |  |  | tiles work
28 | F - 504 | 26-05-21 | 02-11-21 | 25-03-22 |  |  | tiles work
29 | F - 505 | 14-01-21 | 16-09-21 | 25-03-22 |  |  | putty work
30 | F - 506 | 14-11-20 | 19-03-21 | 14-02-22 | 15-06-22
31 | F - 601 | 14-11-20 | 07-08-21 | 28-04-22 |  |  | putty work
32 | F - 602 | 14-01-21 | 20-10-21 | 28-04-22 |  |  | putty work
33 | F - 603 | 31-05-21 | 28-11-21 | 28-04-22 |  |  | putty work
34 | F - 604 | 26-05-21 | 28-11-21 | 28-04-22 |  |  | putty work
35 | F - 605 | 14-01-21 | 20-10-21 | 28-04-22 |  |  | putty work
36 | F - 606 | 14-11-20 | 07-08-21 | 28-04-22 |  |  | putty work

## G-Block
Company Name Modiproperties.Pvt Ltd
Project |  | GULMOHAR RESDIENCY
Prepared By
Last updated on |  | 28-06-22
Block No |  | Block - G
S.No | Flat No | Plinth beam casting Date | Slab casting date | Stage - I BW & internal plastering completion date | Stage II Completion date (Fooring, Bathroom Tiles, 1st Coat Painting) | Stage III completion date | Remarks
1 | G - 101 | 06-03-21 | 25-08-21 | 14-03-22
2 | G - 102 | 27-03-21 | 30-08-21 | 28-02-22
3 | G - 103 | 14-06-21 | 30-08-21 | 28-02-22
4 | G - 104 | 14-06-21 | 30-08-21 | 14-03-22
5 | G - 105 | 27-03-21 | 30-08-21 | 28-02-22
6 | G - 106 | 06-03-21 | 25-08-21 | 14-03-22
7 | G - 107 | 06-03-21 | 25-08-21 | 18-05-22
8 | G - 201 | 06-03-21 | 19-10-21 | 27-04-22
9 | G - 202 | 27-03-21 | 19-10-21 |  |  |  | plastering in progress
10 | G - 203 | 14-06-21 | 19-10-21 | 27-04-22
11 | G - 204 | 14-06-21 | 19-10-21 | 27-04-22
12 | G - 205 | 27-03-21 | 19-10-21 | 15-05-22
13 | G - 206 | 06-03-21 | 19-10-21 | 15-05-22
14 | G - 207 | 06-03-21 | 19-10-21 | 15-05-22
15 | G - 301 | 06-03-21 | 26-10-21 | 25-03-22
16 | G - 302 | 27-03-21 | 26-10-21 | 14-03-22
17 | G - 303 | 14-06-21 | 26-10-21 | 14-03-22
18 | G - 304 | 14-06-21 | 26-10-21 | 25-03-22
19 | G - 305 | 27-03-21 | 26-10-21 | 14-03-22
20 | G - 306 | 06-03-21 | 26-10-21 | 25-03-22
21 | G - 307 | 06-03-21 | 26-10-21 | 25-03-22
22 | G - 401 | 06-03-21 | 10-11-21 | 15-05-22
23 | G - 402 | 27-03-21 | 10-11-21 |  |  |  | plastering in progress
24 | G - 403 | 14-06-21 | 10-11-21 |  |  |  | plastering in progress
25 | G - 404 | 14-06-21 | 10-11-21 |  |  |  | plastering in progress
26 | G - 405 | 27-03-21 | 10-11-21 |  |  |  | brickwork in progress
27 | G - 406 | 06-03-21 | 10-11-21 |  |  |  | plastering in progress
28 | G - 407 | 06-03-21 | 10-11-21 |  |  |  | brickwork in progress
29 | G - 501 | 06-03-21 | 22-12-21 |  |  |  | brickwork in progress
30 | G - 502 | 27-03-21 | 22-12-21 |  |  |  | brickwork in progress
31 | G - 503 | 14-06-21 | 22-12-21 |  |  |  | brickwork in progress
32 | G - 504 | 14-06-21 | 22-12-21 |  |  |  | brickwork in progress
33 | G - 505 | 27-03-21 | 22-12-21 |  |  |  | brickwork in progress
34 | G - 506 | 06-03-21 | 22-12-21 |  |  |  | brickwork in progress
35 | G - 507 | 06-03-21 | 22-12-21 |  |  |  | brickwork in progress
36 | G - 601 | 06-03-21 | 14-02-22 |  |  |  | brickwork in progress
37 | G - 602 | 27-03-21 | 14-02-22 |  |  |  | brickwork in progress
38 | G - 603 | 14-06-21 | 14-02-22 |  |  |  | brickwork in progress
39 | G - 604 | 14-06-21 | 14-02-22 |  |  |  | brickwork in progress
40 | G - 605 | 27-03-21 | 14-02-22 |  |  |  | brickwork in progress
41 | G - 606 | 06-03-21 | 14-02-22 |  |  |  | brickwork in progress
42 | G - 607 | 06-03-21 | 14-02-22 |  |  |  | brickwork in progress

## H-Block
Company Name Modiproperties.Pvt Ltd
Project |  | GULMOHAR RESDIENCY
Prepared By
Last updated on |  | 28-06-22
Block No |  | Block - H
S.No | Flat No | Plinth beam casting Date | Slab casting date | Stage - I BW & internal plastering completion date | Stage II Completion date (Fooring, Bathroom Tiles, 1st Coat Painting) | Stage III completion date | Remarks
1 | H - 101 | 24-12-21 | 09-06-22 |  |  |  | 2nd floor columns
2 | H - 102 | 24-12-21 | 09-06-22 |  |  |  | 2nd floor columns
3 | H - 103 | 24-12-21 | 09-06-22 |  |  |  | 2nd floor columns
4 | H - 104 | 24-12-21 | 09-06-22 |  |  |  | 2nd floor columns
5 | H - 105 | 24-12-21 | 09-06-22 |  |  |  | 2nd floor columns
6 | H - 106 | 24-12-21 | 09-06-22 |  |  |  | 2nd floor columns
7 | H - 107 | 24-12-21 | 09-06-22 |  |  |  | 2nd floor columns
8 | H - 201
9 | H - 202
10 | H - 203
11 | H - 204
12 | H - 205
13 | H - 206
14 | H - 207
15 | H - 301
16 | H - 302
17 | H - 303
18 | H - 304
19 | H - 305
20 | H - 306
21 | H - 307
22 | H - 401
23 | H - 402
24 | H - 403
25 | H - 404
26 | H - 405
27 | H - 406
28 | H - 407
29 | H - 501
30 | H - 502
31 | H - 503
32 | H - 504
33 | H - 505
34 | H - 506
35 | H - 507
36 | H - 601
37 | H - 602
38 | H - 603
39 | H - 604
40 | H - 605
41 | H - 606
42 | H - 607
['