## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-06-25
Site |  | GVRC
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
164836 | 2022-04-12 | Aluminium cladding | Cancelled by Ramesh Reddy engg
164941 | 2022-05-10 | Persnol Computer | Cancelled by MD
206003 | 2022-06-04 | Laptop | Not with MD for approval
206004 | 2022-06-03 | MEP Tools | Requisition missed kindly send
206005 | 2022-06-03 | Cutting player, nose player, screw driver, hammer | PO 89421
206006 | 2022-06-03 | Tool box, lock pipe wrinch, monkey spanner etc., | Estimate to be prepare
206007 | 2022-06-06 | Server PC | Cancelled by MD
206020 | 2022-06-14 | D link router | Online purchase
206022 | 2022-06-14 | Steel grey granite | PO 89267
206023 | 2022-06-14 | Table with low storage unit | PO to be issue
206024 | 2022-06-14 | 4 core armourod cable | PO to be issue
206027 | 2022-06-15 | 75 MM L angle | PO 87246, 89427
206030 | 2022-06-16 | WPC Door frames | PO 89434
206032 | 2022-06-16 | MS powder coating kerbee sheet | PO to be issue
206034 | 2022-06-18 | Flush doors | PO to be issue
206036 | 2022-06-17 | MS Rolling shutters | PO to be issue
206040 | 2022-06-17 | Cutting blades | PO 89457
206044 | 2022-06-21 | SS Railing | PO to be issue
206045 | 2022-06-22 | General items | PO to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
163704 | 2021-08-07 | ACP cladding | Work under progress
164829 | 2022-04-09 | Cera board | Work under process by karunakar,clarification required from madhu to karunakar
164851 | 2022-04-14 | Bathroom door | No response from supplier will get back to you once we speak to supplier
164891 | 2022-04-23 | Aerocon panels | PO with MD sir for approval
164894 | 2022-04-23 | FRD Doors | Supplier will confirm the delivery date
164920 | 2022-05-06 | PU Foam | Pick up from Supplier place
164923 | 2022-05-05 | Luminious inverter battary | Next week delivery
164928 | 2022-05-05 | CCTV Bullet camera | Deliverd
164929 | 2022-05-06 | ACP cladding | Work under process Pinnaccle
164923 | 2022-05-11 | ACP Walls pop work | Work under process
164965 | 2022-05-19 | B calss pipe , flat patti | Pick up from Supplier place
164987 | 2022-05-27 | Galvalume sheet | Pick up from Supplier place
164993 | 2022-05-30 | JBL CSL | Deliverd
206014 | 2022-06-13 | Steel grey granite | Pick up from SOVLLP
206021 | 2022-06-14 | Fire extiunguisher | Pick up from Kothari
206025 | 2022-06-15 | Arm grout inject | Pick up from Anisha
206026 | 2022-06-15 | Steel grey granite | Pick up from SOVLLP
206037 | 2022-06-17 | Adhesive chemical | Pick up from Anisha