## Anx - A - Attendance details (hidden)
Annexure - A - Send Weekly
Details of labour charges
Name of contractor: |  | ASHOK CONSTRUCTION
Company name: |  | MRMLLP
Project name: |  | AVR Gulmohar Homes
Date: |  | 19/3/2020
Period |  | From: | 2020-12-03 | To: | 18/3/2020
Sl. No. | Work Type | Worker Type | Quantity | Rate | Amount
1 | Civil work | Mason | 115.75 | 575 | 66556.25
2 | Civil work | Male helper | 93 | 400 | 37200
3 | Civil work | Female helper | 67 | 350 | 23450
4 | RCC work | Mason |  | 550 | 0
5 | RCC work | Male helper |  | 400 | 0
6 | RCC work | Female helper |  | 0 | 0
7 | Earth work | Mason |  | 0 | 0
8 | Earth work | Male helper |  | 450 | 0
9 | Earth work | Female helper |  | 400 | 0
10 | Electrician | Mason |  | 550 | 0
11 | Electrician | Male helper |  | 400 | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
| Total |  |  |  | 127206.25
Payment approved by MD:
Prepared by: |  |  |  |  | MDs approval
Name | Vijitha
Date | 19/3/2020

## Anx - B - Hire charges (hidden)
Annexure - B - Send Weekly
Details of hire charges
Name of contractor: |  | ASHOK CONSTRUCTIONS
Company name: |  | MRMLLP
Project name: |  | AVR Gulmohar Homes
Date: |  | 19/3/2019
Period |  | From: | 2020-12-03 | To: | 18/3/2020
Sl. No. | Equipment Type | Quantity | Rate | Units | Amount
1 | JCB | 1.683 | 900 | Hour | 1514.7
2 | Tractor | 0 | 1800 | Engage | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
21 |  |  |  |  | 0
22 |  |  |  |  | 0
23 |  |  |  |  | 0
24 |  |  |  |  | 0
25 |  |  |  |  | 0
| Total |  |  |  | 1514.7
Payment approved by MD:
Prepared by: |  |  |  |  | MDs approval
Name | Vijitrha
Date | 19/3/2020

## Anx - C - Material received (hidden)
Annexure - C - send weekly
Details of magterial received
Name of contractor: |  | ASHOK CONSTRUCTIONS
Company name: |  | MRMLLP
Project name: |  | AVR Gulmohar Homes
Date: |  | 19/3/2020
Period |  | From: | 2020-12-03 | To: | 18/3/2020
Sl. No. | Material type | Received date | Inward no. | Quantity | Units | Rate | Amount
1 | STONEDUST | 13/3/2020 | 196 | 21.8 | TONS | 620 | 13516
2 | 20MM | 13/3/2020 | 197 | 23.07 | TONS | 620 | 14303
3 | CEMENT BRICKS (16X8X6) | 13/3/2020 | 418 | 250 | NO'S | 28 | 7000
4 | CEMENT BRICKS (16X8X6) | 18/3/2020 | 419 | 250 | NO'S | 28 | 7000
5 | RED BRICKS | 18/3/2020 | 420 | 3000 | NO'S | 7 | 21000
6 | CEMENT BRICKS (16X8X4) | 18/3/2020 | 421 | 400 | NO'S | 24 | 9600
7 | CEMENT BRICKS (16X8X6) | 18/3/2020 | 422 | 250 | NO'S | 28 | 7000
8
9
10
11
12
13
14
15
16
17
18
19 | [6 empty] | 0
20 | [6 empty] | 0
21 | [6 empty] | 0
22 | [6 empty] | 0
23
24 | [6 empty] | 0
| Total | [5 empty] | 79419
Payment approved by MD:
Prepared by: |  |  |  | Approved by: |  | MDs approval
Name | Vijitha |  |  | Zakir
Date | 19/3/2020 |  |  | 19/3/2020

## Anx - D - Milestone report (hidden)
Annexure - D - send weekly
Mile stone report for CR-
Company name: |  |  |  | MRMLLP
Project name: |  |  |  | AVR Gulmohar Homes
Date: |  |  |  | 19/3/2020
Note: | Prepare the statement for all the villas in the project.
S No | Villa no- | Type (2, 3, 4BHK) | SBUA | Work start date | Completion of plinth | Completion of RCC | Completion of brickwork and plastering | Completion of stage I | Completion of stage II | Completion of stage III | Completion of stage IV | Date of physical posession
1 | 1 | 3BHK | 2340 | 2019-08-09 | 2019-10-16 | 2020-01-11
2 | 2 | 4BHK | 2340 | 2017-04-27 | 2017-08-08 | 2018-01-02 | 2018-04-10 | 2018-08-09 | 2018-08-14 | 2018-08-14 | 2018-09-07
3 | 3 | 2BHK | 1250 | 2017-04-27 | 2017-02-09 | 29/12/2017 | 2018-04-10 | 2019-05-17 | 2018-09-01 | 2018-09-07 | 2018-11-11
4 | 4 | 2BHK | 1250 | 2017-04-27 | 2017-08-16 | 29/12/2017 | 2018-04-24
5 | 5 | 2BHK | 1250 | 2017-04-27 | 2017-08-16 | 2018-01-06 | 2018-05-08
6 | 6 | 3BHK | 2340 | 2017-04-27 | 2017-08-16 | 2018-05-22 | 2019-04-01
7 | 7 | 3BHK | 2340 | 2017-04-27 | 2017-08-16 | 2018-05-29 | 2019-04-25 | 2020-03-07
8 | 92 | 3BHK | 2340 | 2017-11-18 | 2018-07-04 | 2018-12-11 | 2019-11-14
9 | 9 | 2 BHK | 1250 | 2017-09-16 | 2017-10-11 | 2018-01-06 | 2018-05-15 | 2018-11-06 | 2019-03-27 | 2019-07-19
10 | 10 | 2BHK | 1250 | 2018-08-18 | 2018-10-29 | 2019-01-03 | 2020-01-10
11 | 11 | 2BHK | 1250 | 2018-08-19 | 2018-10-24 | 2018-12-20 | 2019-07-20
12 | 12 | 2BHK | 1250 | 2018-07-30 | 2018-09-10 | 13-11-2018
13 | 13 | 2 BHK | 1250 | 2018-07-04 | 2018-09-10 | 2018-11-01
14 | 14 | 2 BHK | 1250 | 2018-07-04 | 2018-11-20 | 2019-01-11
15 | 15 | 3BHK | 2340 | 2018-08-29 | 30/07/2019 | 2019-08-12
16 | 16 | 3BHK | 2340 | 2018-07-11 | 2018-11-22 | 2019-02-07
17 | 17 | 2BHK | 1250 | 2018-08-06 | 2018-12-06 | 2019-01-30 | 2020-01-10
18 | 18 | 3BHK | 2340 | 2019-07-29 | 2019-11-20
19 | 19 | 3BHK | 2340 | 2019-07-31 | 2019-11-23
20 | 20 | 2BHK | 1250 | 2018-08-27 | 2019-01-05 | 2019-02-11
21 | 21 | 2 BHK | 1250 | 2017-09-16 | 2017-10-12 | 2018-01-30 | 2018-05-19 | 2018-12-04 | 2019-03-31 | 2019-07-23
22 | 22 | 2 BHK | 1250 | 2017-05-30 | 2017-11-20 | 2018-01-30 | 2018-05-26 | 2018-08-18 | 2019-03-07 | 2019-08-14
23 | 23 | 3BHK | 2340 | 2018-07-23 | 2019-02-08 | 2019-06-25
24 | 24 | 3BHK | 2340 | 2019-07-31
25 | 25 | 3BHK | 2340 | 2019-08-07 | 2020-01-04
26 | 26 | 3BHK | 2264.52 | 2019-05-23
27 | 27 | 3BHK | 2340 | 2018-08-08 | 2018-11-24
28 | 28 | 3BHK | 2340 | 2018-08-07 | 2018-11-27
29 | 29 | 2BHK | 1250 | 2018-12-25 | 2019-02-03 | 2019-02-28 | 2019-09-02 | 2020-02-15
30 | 30 | 2 BHK | 1250 | 2017-05-30 | 2017-11-23 | 2018-03-21 | 2018-11-30 | 2019-01-30 | 2019-04-25 | 2019-08-14
31 | 31 | 2BHK | 1250 | 2018-12-26 | 2019-02-06 | 2019-03-16 | 2019-12-20
32 | 32 | 4 BHK | 2340 | 2017-07-28 | 2017-12-19 | 2018-02-23 | 2018-06-13 | 2019-11-06 | 2019-06-18 | 2019-08-16
33 | 33 | 2BHK | 1250 | 2019-04-23 | 14/06/2019 | 2019-02-08 | 2019-12-17 | 2020-02-06
34 | 34 | 2 BHK | 1250 | 2018-07-09 | 12.06.2019 | 2019-07-16 | 2019-11-15 | 2020-01-28
35 | 35 | 2 BHK | 1250 | 2017-09-15 | 2017-10-07 | 2018-01-07 | 2018-09-27 | 2018-11-13 | 2019-10-16 | 2019-12-19
36 | 36 | 3BHK | 2340 | 2018-08-25 | 2019-09-19 | 28/01/2020
37 | 37 | 2BHK | 1250 | 2017-07-24 | 2017-11-28 | 2018-01-09 | 2018-12-11 | 2019-06-19 | 2019-10-30 | 2019-12-20
38 | 38 | 4 BHK | 2340 | 2019-01-07 | 2019-02-25 | 2019-04-09 | 2020-01-10
39 | 39 | 4BHK | 2340 | 2019-01-07 | 2019-02-23 | 2019-03-30 | 2020-01-10
40 | 40 | 3-BHK | 2340 | 2018-06-10 | 2018-07-10 | 2019-02-23
41 | 41 | 2-BHK | 1250 | 2018-06-05 | 2018-06-27 | 2018-10-03 | 2019-06-18 | 2020-02-11 | 2020-02-15
42 | 42 | 3BHK | 2340 | 2018-07-20 | 2019-11-12
43 | 43 | 3BHK | 2340 | 2019-07-25 | 2019-11-14 | 2019-12-21
44 | 44 | 2 BHK | 1250 | 2019-05-29 | 2019-10-30 | 2020-02-15
45 | 45 | 3BHK | 2340 | 2019-07-11 | 2019-10-25
46 | 46 | 3BHK | 2340 | 2019-07-10 | 2019-10-16
47 | 47 | 3BHK | 2340 | 2019-04-28 | 2019-09-27 | 2019-11-19
48 | 48 | 2 BHK | 1250 | 2017-09-15 | 2017-10-26 | 2018-03-08 | 2018-07-03 | 2018-11-13 | 2019-05-10 | 2019-08-27
49 | 49 | 3BHK | 2340 | 2019-07-06 | 2019-08-19 | 2019-12-20
50 | 50 | 4 BHK | 2340 | 2019-06-04 | 2019-09-20 | 2020-02-06
51 | 51 | 3BHK | 2340 | 25/06/2019 | 2019-08-26
52 | 52 | 3BHK | 2340 | 2019-06-26 | 2019-09-06
53 | 53 | 2BHK | 1250 | 2019-05-29 | 2019-09-06 | 2020-02-15
54 | 54 | 3BHK | 2340 | 2019-07-09 | 2019-09-28 | 2020-03-07
55 | 55 | 4BHK | 2430 | 2018-07-21 | 2019-08-16 | 2019-11-05
56 | 56 | 2 BHK | 1250 | 2018-07-21 | 2019-01-03 | 2019-07-26
57 | 57 | 2 BHK | 1250 | 2017-10-16 | 2017-12-09 | 2018-03-24 | 2019-02-19 | 2019-09-17 | 2019-11-14 | 2019-12-19
58 | 58 | 2 BHK | 1250 | 2018-07-18 | 2018-08-22
59 | 59 | 4BHK | 2340 | 2019-05-16 | 2019-07-09 | 2019-09-11
60 | 60 | 2BHK | 1250 | 2018-07-21 | 2018-08-21 | 2019-07-14
61 | 61 | 2 BHK | 1250 | 2017-09-15 | 2017-10-14 | 2018-04-17 | 2018-09-29 | 2018-11-22 | 2019-05-22 | 2019-08-27
62 | 62 | 2 BHK | 1250 | 2017-07-24 | 2017-12-23 | 2018-03-19 | 2018-11-15 | 2019-01-30 | 2019-06-29 | 2019-09-24
63 | 63 | 2 BHK | 1250 | 2017-11-08 | 2017-12-25 | 2018-03-06 | 2018-11-15 | 2019-02-19 | 2019-09-24 | 2019-10-05
64 | 64 | 2 BHK | 1250 | 2017-09-15 | 2017-10-14 | 2018-02-23 | 2018-11-15 | 2019-02-19 | 2019-06-18 | 2019-09-28
65 | 65 | 3BHK | 2340 | 2018-06-15 | 2018-07-21 | 2018-11-13 | 2019-09-06
66 | 66 | 3BHK | 2340 | 2018-06-07 | 2018-07-07 | 2018-12-05 | 2019-09-06
67 | 67 | 3BHK | 2340 | 2018-06-16 | 2018-07-25
68 | 68 | 3BHK | 2340 | 2018-12-23 | 2019-01-19 | 2019-11-14
69 | 69 | 3BHK | 2340 | 2018-06-14 | 2018-07-26 | 2019-07-30
70 | 70 | 3BHK | 2340 | 2018-06-14 | 2018-07-28 | 2019-07-30
71 | 71 | 2 BHK | 1250 | 2017-07-31 | 2018-07-09 | 2018-09-05 | 2020-01-10
72 | 72 | 2BHK | 1250 | 2018-07-02 | 15-11-2018
73 | 73 | 2 BHK | 1250 | 2018-07-05 | 2018-08-04 | 2018-10-10
74 | 74 | 2 BHK | 1250 | 2017-09-15 | 2017-11-14 | 2018-04-03 | 2018-12-21 | 2019-05-24 | 2019-11-16 | 2020-01-11
75 | 75 | 2 BHK | 1250 | 2018-05-18 | 2018-06-20 | 2018-09-19 | 2019-06-11 | 2019-09-19 | 2019-11-14 | 23/01/2020
76 | 76 | 2 BHK | 1250 | 2017-11-08 | 2017-12-19 | 2018-04-03 | 2019-03-02 | 2019-04-25 | 2019-12-02 | 2020-01-28
77 | 77 | 2BHK | 1250 | 2017-11-30 | 2018-03-31 | 2018-05-16 | 2018-11-30 | 2019-04-25 | 2019-09-13 | 2019-10-05
78 | 78 | 2BHK | 1250 | 2019-05-07 | 2019-07-05 | 2019-08-17 | 2020-01-10 | 2020-02-15
79 | 79 | 2 BHK | 1250 | 2017-10-26 | 2017-12-04 | 2018-03-24 | 2018-12-15 | 2019-05-10
80 | 80 | 2 BHK | 1250 | 2017-10-26 | 2017-12-13 | 2018-03-24 | 2018-12-04 | 2019-05-22 | 2019-09-17 | 2019-10-04
81 | 81 | 3BHK | 2340 | 2018-06-21 | 2018-08-07 | 2019-09-19
82 | 82 | 3BHK | 2340 | 2018-06-18 | 2018-08-24 | 2019-09-03
83 | 83 | 2BHK | 1250 | 2019-05-14 | 18/06/2019 | 2019-10-01 | 2020-01-10
84 | 84 | 2 BHK | 1250 | 2018-06-26 | 2018-08-25 | 2018-11-07
85 | 85 | 3BHK | 2340 | 2019-05-16 | 2019-07-06 | 2019-12-13
86 | 86 | 2 BHK | 1250 | 2017-12-13 | 2018-06-13 | 2018-08-23 | 2019-05-10 | 2019-11-05 | 2020-01-28
87 | 87 | 2 BHK | 1250 | 2018-06-25 | 2018-08-30 | 2018-12-26 | 2019-10-18 | 2019-11-28 | 2020-02-01
88 | 88 | 2 BHK | 1250 | 2017-10-26 | 2017-11-30 | 2018-06-05 | 2019-09-17 | 2019-12-13 | 2020-01-28
89 | 89 | 3BHK | 2340 | 2019-06-03 | 2019-09-24 | 2019-12-13
90 | 90 | 3BHK | 2340 | 2019-06-24 | 2019-09-24 | 2019-11-06 | 2019-05-10 | 2019-10-10 | 2020-01-21
91 | 91 | 2BHK | 1250 | 2017-09-15 | 2018-04-17 | 2018-11-07 | 2019-05-10 | 2020-03-18

## Anx - E1 -Estimate of work done
Annexure - E1 - Details of partial work done and not yet billed - send on the last Saturday of the month-
Name of contractor: |  |  |  | ASHOK CONSTRUCTIONS
Company name: |  |  |  | MRMLLP
Project name: |  |  |  | AVR Gulmohar Homes
Date: |  |  |  | 2022-06-29
Note: | Enter value beween 1&100 as approximate pecentage of work completed- Enter 0 where work is completed and billed.
|  | Rate |  |  | 20 | 25 | 25 | 20 | 10 | 100
S No | Villa no- | Type (2, 3, 4BHK) | SBUA | Work start date | Earth work, footing, plinth, column1 | RRC, slabs + head room | Brick work, compound wall & site levelling | 2 coats plastering | Final finishing and handover | Total percentage of work done | Rate per sft | Construction contract value | Value of work done
1 | 1 | 3BHK | 2340 | 2019-08-09 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
2 | 2 | 4BHK | 2340 | 2017-10-15 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 1638000 | 0
3 | 3 | 2BHK | 1250 | 2017-10-15 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
4 | 4 | 2BHK | 2340 | 2017-10-15 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 1813500 | 0
5 | 5 | 2BHK | 1250 | 2017-11-18 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
6 | 6 | 3BHK | 2340 | 2018-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
7 | 7 | 3BHK | 2340 | 2018-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
8 | 9 | 2BHK | 1250 | 2017-11-18 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
9 | 10 | 2BHK | 1250 | 2018-09-16 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
10 | 11 | 2BHK | 1250 | 2018-08-18 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
11 | 12 | 2BHK | 1250 | 2018-08-18 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
12 | 13 | 2BHK | 1250 | 2018-07-30 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
13 | 14 | 2BHK | 1250 | 2018-07-04 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
14 | 15 | 3BHK | 2340 | 2018-07-04 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
15 | 16 | 3BHK | 2340 | 2018-08-29 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
16 | 17 | 2BHK | 1250 | 2018-07-11 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
17 | 18 | 3BHK | 2340 | 2018-08-08 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
18 | 19 | 3BHK | 2340 | 2019-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
19 | 20 | 2BHK | 1250 | 2019-08-27 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
20 | 21 | 2BHK | 1250 | 2018-08-27 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
21 | 22 | 2BHK | 1250 | 2017-09-16 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
22 | 23 | 3BHK | 2340 | 2018-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
23 | 24 | 3BHK | 1250 | 2018-07-23 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 937500 | 0
24 | 25 | 3BHK | 2340 | 2019-08-07 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
25 | 26 | 3BHK | 2340 | 2018-08-06 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
26 | 27 | 3BHK | 2340 | 2018-08-06 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
27 | 28 | 3BHK | 2340 | 2018-08-08 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
28 | 29 | 2BHK | 1250 | 2018-08-07 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
29 | 30 | 2BHK | 1250 | 2018-12-25 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
30 | 31 | 2BHK | 1250 | 2017-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
31 | 32 | 4BHK | 2340 | 2018-12-26 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 1638000 | 0
32 | 33 | 2BHK | 1250 | 2017-10-25 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
33 | 34 | 2BHK | 1250 | 2019-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
34 | 35 | 2BHK | 1250 | 2018-07-09 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
35 | 36 | 3BHK | 2340 | 2017-09-16 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
36 | 37 | 2BHK | 1250 | 2018-08-25 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
37 | 38 | 4BHK | 2340 | 2017-10-25 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 1638000 | 0
38 | 39 | 4BHK | 2340 | 2019-01-07 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 1638000 | 0
39 | 40 | 3BHK | 2340 | 2019-01-07 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
40 | 41 | 2BHK | 1250 | 2018-06-10 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
41 | 42 | 3BHK | 2340 | 2018-06-05 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
42 | 43 | 3BHK | 2340 | 2018-07-27 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
43 | 44 | 2BHK | 1250 | 2019-05-29 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
44 | 45 | 3BHK | 2340 | 2019-07-11 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
45 | 46 | 3BHK | 2340 | 2019-07-10 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
46 | 47 | 3BHK | 2340 | 2019-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
47 | 48 | 2BHK | 1250 | 2017-09-15 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
48 | 49 | 3BHK | 2340 | 2017-09-16 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
49 | 50 | 2BHK | 1250 | 2019-06-04 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
50 | 51 | 3BHK | 2340 | 2019-07-26 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
51 | 52 | 3BHK | 2340 | 2019-07-25 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
52 | 53 | 2BHK | 1250 | 2019-05-29 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
53 | 54 | 3BHK | 2340 | 2019-07-09 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
54 | 55 | 4BHK | 2340 | 2018-07-21 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 1638000 | 0
55 | 56 | 2BHK | 1250 | 2018-07-21 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
56 | 57 | 2BHK | 1250 | 2018-07-21 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
57 | 58 | 4BHK | 2340 | 2017-09-16 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 1638000 | 0
58 | 59 | 4BHK | 2340 | 2018-07-18 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 1638000 | 0
59 | 60 | 2BHK | 1250 | 2018-07-21 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
60 | 61 | 2BHK | 1250 | 2018-07-21 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
61 | 62 | 2BHK | 1250 | 2017-09-16 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
62 | 63 | 2BHK | 1250 | 2017-10-25 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
63 | 64 | 2BHK | 1250 | 2017-11-08 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
64 | 65 | 3BHK | 2340 | 2017-09-16 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
65 | 66 | 3BHK | 2340 | 2018-06-22 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
66 | 67 | 3BHK | 2340 | 2018-06-07 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
67 | 68 | 3BHK | 2340 | 2018-06-16 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
68 | 69 | 3BHK | 2340 | 2018-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
69 | 70 | 3BHK | 2340 | 2018-06-14 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
70 | 71 | 2BHK | 1250 | 2018-06-14 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
71 | 72 | 4BHK | 2340 | 2017-10-25 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 1638000 | 0
72 | 73 | 4BHK | 2340 | 2018-07-02 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 1638000 | 0
73 | 74 | 2BHK | 1250 | 2018-07-05 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
74 | 75 | 2BHK | 1250 | 2017-09-16 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
75 | 76 | 2BHK | 1250 | 2018-05-18 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
76 | 77 | 2BHK | 1250 | 2017-10-26 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
77 | 78 | 2BHK | 1250 | 2017-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
78 | 79 | 2BHK | 1250 | 2017-10-26 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
79 | 80 | 2BHK | 1250 | 2017-10-26 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
80 | 81 | 3BHK | 2340 | 2017-10-26 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
81 | 82 | 3BHK | 2340 | 2018-06-21 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
82 | 83 | 2BHK | 1250 | 2018-06-18 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
83 | 84 | 2BHK | 1250 | 2018-06-26 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
84 | 85 | 3BHK | 2340 | 2018-06-26 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
85 | 86 | 2BHK | 1250 | 2017-12-13 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
86 | 87 | 2BHK | 1250 | 2017-12-13 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
87 | 88 | 2BHK | 1250 | 2018-06-25 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
88 | 89 | 3BHK | 2340 | 2017-10-26 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
89 | 90 | 3BHK | 2340 | 2019-06-19 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
90 | 91 | 2BHK | 1250 | 2017-09-16 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 968750 | 0
91 | 92 | 3BHK | 2340 | 2017-09-16 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1755000 | 0
92 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total | 162800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 626.8182 | 122511750 | 0

## Anx - E2 - work done & billed
Annexure - E2 - work completed and bill raised -send on the last Saturday of the month. | [14 empty] | 0
Name of contractor: |  |  |  | ASHOK CONSTRUCTIONS
Company name: |  |  |  | MRMLLP
Project name: |  |  |  | AVR Gulmohar Homes
Date: |  |  |  | 2022-06-29
Note: | Enter vlaue 1 if work is completed and billed. Enter 0 otherwise. This statement must match billing database.
|  | Rate |  |  | 20 | 25 | 25 | 20 | 10 | 100 |  |  | 0
S No | Villa no. | Type (2, 3, 4BHK) | SBUA | Work start date | Earth work, footing, plinth, column1 | RRC, slabs + head room | Brick work, compound wall & site levelling | 2 coats plastering | Final finishing and handover | Total percentage of work done | Rate per sft | GST | Construction contract value | Value of work done | Advance Paid | Advance adjusted
1 | 1 | 3BHK | 2340 | 2019-08-09 | 1 | 1 | 1 | 1 | 1 | 100 | 750 | 18 | 2070900 | 2070900 | 100000 | 100000
2 | 2 | 4BHK | 2340 | 2017-10-15 | 1 | 1 | 1 | 1 | 1 | 100 | 700 | 18 | 1932840 | 1932840 | 100000 | 100000
3 | 3 | 2BHK | 1250 | 2017-10-15 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
4 | 4 | 2BHK | 1250 | 2017-10-15 | 1 | 1 | 1 | 1 | 0 | 90 | 775 | 18 | 1143125 | 1028812.5 | 100000 | 90000
5 | 5 | 2BHK | 1250 | 2017-11-18 | 1 | 1 | 1 | 1 | 0 | 90 | 775 | 18 | 1143125 | 1028812.5 | 100000 | 90000
6 | 6 | 3BHK | 2340 | 2018-03-28 | 1 | 1 | 1 | 1 | 1 | 100 | 750 | 18 | 2070900 | 2070900 | 100000 | 100000
7 | 7 | 3BHK | 2340 | 2018-03-28 | 1 | 1 | 1 | 1 | 1 | 100 | 750 | 18 | 2070900 | 2070900 | 100000 | 100000
8 | 9 | 2BHK | 1250 | 2017-11-18 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
9 | 10 | 2BHK | 1250 | 2018-09-16 | 1 | 1 | 1 | 1 | 0 | 90 | 775 | 18 | 1143125 | 1028812.5 | 100000 | 90000
10 | 11 | 2BHK | 1250 | 2018-08-18 | 1 | 1 | 1 | 1 | 0 | 90 | 775 | 18 | 1143125 | 1028812.5 | 100000 | 90000
11 | 12 | 2BHK | 1250 | 2018-08-18 | 1 | 1 | 1 | 1 | 0 | 90 | 775 | 18 | 1143125 | 1028812.5 | 100000 | 90000
12 | 13 | 2BHK | 1250 | 2018-07-30 | 1 | 1 | 1 | 1 | 0 | 90 | 775 | 18 | 1143125 | 1028812.5 | 100000 | 90000
13 | 14 | 2BHK | 1250 | 2018-07-04 | 1 | 1 | 1 | 1 | 0 | 90 | 775 | 18 | 1143125 | 1028812.5 | 100000 | 90000
14 | 15 | 3BHK | 2340 | 2018-07-04 | 1 | 1 | 1 | 1 | 1 | 100 | 750 | 18 | 2070900 | 2070900 | 100000 | 100000
15 | 16 | 3BHK | 2340 | 2018-08-29 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
16 | 17 | 2BHK | 1250 | 2018-07-11 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
17 | 18 | 3BHK | 2340 | 2018-08-08 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
18 | 19 | 3BHK | 2340 | 2019-07-31 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
19 | 20 | 2BHK | 1250 | 2019-08-27 | 1 | 1 | 1 | 1 | 0 | 90 | 775 | 18 | 1143125 | 1028812.5 | 100000 | 90000
20 | 21 | 2BHK | 1250 | 2018-08-27 | 1 | 1 | 1 | 1 | 0 | 90 | 775 | 18 | 1143125 | 1028812.5 | 100000 | 90000
21 | 22 | 2BHK | 1250 | 2017-09-16 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
22 | 23 | 3BHK | 2340 | 2018-05-30 | 1 | 1 | 1 | 1 | 1 | 100 | 750 | 18 | 2070900 | 2070900 | 100000 | 100000
23 | 24 | 3BHK | 2340 | 2018-07-23 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
24 | 25 | 3BHK | 2340 | 2019-08-07 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
25 | 26 | 3BHK | 2340 | 2018-08-06 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
26 | 27 | 3BHK | 2340 | 2018-08-06 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
27 | 28 | 3BHK | 2340 | 2018-08-08 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
28 | 29 | 2BHK | 1250 | 2018-08-07 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
29 | 30 | 2BHK | 1250 | 2018-12-25 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
30 | 31 | 2BHK | 1250 | 2017-05-30 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
31 | 32 | 4BHK | 2340 | 2018-12-26 | 1 | 1 | 1 | 1 | 1 | 100 | 700 | 18 | 1932840 | 1932840 | 100000 | 100000
32 | 33 | 2BHK | 1250 | 2017-10-25 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
33 | 34 | 2BHK | 1250 | 2019-04-20 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
34 | 35 | 2BHK | 1250 | 2018-07-09 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
35 | 36 | 3BHK | 2340 | 2017-09-16 | 1 | 1 | 1 | 1 | 1 | 100 | 750 | 18 | 2070900 | 2070900 | 100000 | 100000
36 | 37 | 2BHK | 1250 | 2018-08-25 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
37 | 38 | 4BHK | 2340 | 2017-10-25 | 1 | 1 | 1 | 1 | 1 | 100 | 700 | 18 | 1932840 | 1932840 | 100000 | 100000
38 | 39 | 4BHK | 2340 | 2019-01-07 | 1 | 1 | 1 | 1 | 1 | 100 | 700 | 18 | 1932840 | 1932840 | 100000 | 100000
39 | 40 | 3BHK | 2340 | 2019-01-07 | 1 | 1 | 1 | 1 | 1 | 100 | 750 | 18 | 2070900 | 2070900 | 100000 | 100000
40 | 41 | 2BHK | 1250 | 2018-06-10 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
41 | 42 | 3BHK | 2340 | 2018-06-05 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
42 | 43 | 3BHK | 2340 | 2018-07-27 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
43 | 44 | 2BHK | 1250 | 2019-05-29 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
44 | 45 | 3BHK | 2340 | 2019-07-11 | 1 | 1 | 1 | 1 | 1 | 100 | 750 | 18 | 2070900 | 2070900 | 100000 | 100000
45 | 46 | 3BHK | 2340 | 2019-07-10 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
46 | 47 | 3BHK | 2340 | 2019-04-28 | 1 | 1 | 1 | 1 | 1 | 100 | 750 | 18 | 2070900 | 2070900 | 100000 | 100000
47 | 48 | 2BHK | 1250 | 2017-09-15 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
48 | 49 | 3BHK | 2340 | 2017-09-16 | 1 | 1 | 1 | 1 | 1 | 100 | 750 | 18 | 2070900 | 2070900 | 100000 | 100000
49 | 50 | 2BHK | 1250 | 2019-06-04 | 1 | 1 | 1 | 1 | 0 | 90 | 775 | 18 | 1143125 | 1028812.5 | 100000 | 90000
50 | 51 | 3BHK | 2340 | 2019-07-26 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
51 | 52 | 3BHK | 2340 | 2019-07-25 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
52 | 53 | 2BHK | 1250 | 2019-05-29 | 1 | 1 | 1 | 1 | 0 | 90 | 775 | 18 | 1143125 | 1028812.5 | 100000 | 90000
53 | 54 | 3BHK | 2340 | 2019-07-09 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
54 | 55 | 4BHK | 2340 | 2018-07-21 | 1 | 1 | 1 | 1 | 1 | 100 | 700 | 18 | 1932840 | 1932840 | 100000 | 100000
55 | 56 | 2BHK | 1250 | 2018-07-21 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
56 | 57 | 2BHK | 1250 | 2018-07-21 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
57 | 58 | 4BHK | 2340 | 2017-09-16 | 1 | 1 | 1 | 1 | 0 | 90 | 700 | 18 | 1932840 | 1739556 | 100000 | 90000
58 | 59 | 4BHK | 2340 | 2018-07-18 | 1 | 1 | 1 | 1 | 1 | 100 | 700 | 18 | 1932840 | 1932840 | 100000 | 100000
59 | 60 | 2BHK | 1250 | 2018-07-21 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
60 | 61 | 2BHK | 1250 | 2018-07-21 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
61 | 62 | 2BHK | 1250 | 2017-09-16 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
62 | 63 | 2BHK | 1250 | 2017-10-25 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
63 | 64 | 2BHK | 1250 | 2017-11-08 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
64 | 65 | 3BHK | 2340 | 2017-09-16 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
65 | 66 | 3BHK | 2340 | 2018-06-22 | 1 | 1 | 1 | 1 | 1 | 100 | 750 | 18 | 2070900 | 2070900 | 100000 | 100000
66 | 67 | 3BHK | 2340 | 2018-06-07 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
67 | 68 | 3BHK | 2340 | 2018-06-16 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
68 | 69 | 3BHK | 2340 | 2018-12-15 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
69 | 70 | 3BHK | 2340 | 2018-06-14 | 1 | 1 | 1 | 1 | 1 | 100 | 750 | 18 | 2070900 | 2070900 | 100000 | 100000
70 | 71 | 2BHK | 1250 | 2018-06-14 | 1 | 1 | 1 | 1 | 0 | 90 | 775 | 18 | 1143125 | 1028812.5 | 100000 | 90000
71 | 72 | 4BHK | 2340 | 2017-10-25 | 1 | 1 | 1 | 1 | 0 | 90 | 700 | 18 | 1932840 | 1739556 | 100000 | 90000
72 | 73 | 4BHK | 2340 | 2018-07-02 | 1 | 1 | 1 | 1 | 0 | 90 | 700 | 18 | 1932840 | 1739556 | 100000 | 90000
73 | 74 | 2BHK | 1250 | 2018-07-05 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
74 | 75 | 2BHK | 1250 | 2017-09-16 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
75 | 76 | 2BHK | 1250 | 2018-05-18 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
76 | 77 | 2BHK | 1250 | 2017-10-26 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
77 | 78 | 2BHK | 1250 | 2017-11-30 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
78 | 79 | 2BHK | 1250 | 2017-10-26 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
79 | 80 | 2BHK | 1250 | 2017-10-26 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
80 | 81 | 3BHK | 2340 | 2017-10-26 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
81 | 82 | 3BHK | 2340 | 2018-06-21 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
82 | 83 | 2BHK | 1250 | 2018-06-18 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
83 | 84 | 2BHK | 1250 | 2018-06-26 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
84 | 85 | 3BHK | 2340 | 2018-06-26 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
85 | 86 | 2BHK | 1250 | 2017-12-13 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
86 | 87 | 2BHK | 1250 | 2017-12-13 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
87 | 88 | 2BHK | 1250 | 2018-06-25 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
88 | 89 | 3BHK | 2340 | 2017-10-26 | 1 | 1 | 1 | 1 | 0 | 90 | 750 | 18 | 2070900 | 1863810 | 100000 | 90000
89 | 90 | 3BHK | 2340 | 2019-06-19 | 1 | 1 | 1 | 1 | 1 | 100 | 750 | 18 | 2070900 | 2070900 | 100000 | 100000
90 | 91 | 2BHK | 1250 | 2017-09-16 | 1 | 1 | 1 | 1 | 1 | 100 | 775 | 18 | 1143125 | 1143125 | 100000 | 100000
91 | 92 | 3BHK | 2340 | 2017-09-16 | 1 | 1 | 1 | 1 | 1 | 100 | 750 | 18 | 2070900 | 2070900 | 100000 | 100000
92 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total | 162800 |  | 91 | 91 | 91 | 91 | 54 | 79.3636 | 626.8182 | 14.8909 | 144531710 | 138024128 | 9100000 | 8730000

## Anx - F -Summary of accounts -
Annexure - F - Summary of accounts - ( Provisional )
Name of contractor: ASHOK CONSTRUCTIONS
Company Name: Modi Realty Miryalaguda LLP
Project Name: AVR Gulmohar Homes
Date: | 2022-06-24
S No | Summary - of credits | Amount
1 | Work completed & billed | 138024129
2 | Work Done & Unbilled - Excl GST ** | 2723750
3 | Extra Works - Approved Value | 171931
4 | Payment for increase in rate form 01-04-2017 to 31-12-2018 - Incl GST | 2737297
5 | Payment for increase in rate form 01-01-2019 to 31-03-2019 - Incl GST | 480065
6 | Payment for increase in rate form 01-04-2019 to 30-06-2019 - Incl GST | 746677
7 | Payment for increase in rate form 01-07-2019 to 30-09-2019 - Incl GST | 765929
8 | Payment for increase in rate form 01-10-2019 to 31-12-2019 - Incl GST | 418203
9 | Payment for increase in rate form 01-01-2020 to 31-03-2020 - Incl GST | 525206
10 | Payment for increase in rate form 01-10-2019 to 31-12-2019 - Incl GST | 239443
11 | Payment for increase in rate form 01-04-2020 to 30-06-2020 - Incl GST | 634152
12 | Payment for increase in rate form 01-07-2020 to 30-09-2020 - Not Approved Incl GST* | 290906
13 | Payment for increase in rate form 01-10-2020 to 30-12-2020 - Not Approved Incl GST * | 584220
14 | Extra Works - Not Approved - Incl GST * | 650729
15 | Club house - Billed & Approved value - Incl GST | 8644920
16 | Club house - unbilled value - approx. | 0
| Total A | 157637557
S No | Summary - of debits | Amount
1 | Mobilization advance adjusted | 0
2 | Amount paid | 133695265
3 | Other debits : Labour Quarters Room Rent F.Y : 17-18 | 55962
4 | Labour Quarters Room Rent 18-19 | 173815
5 | Labour Quarters Room Rent 19-20 | 256973
6 | Villa no.30 / 71 / 37 /62 Excavation & Footing Column of 9.65Lac Approved | 127392
7 | Labour Quarters Room Rent & Other Debits 2020 -2021 | 519370
8 | Labour Quarters Room Rent & Other Debits 2021-22 | 364820
9 | Material Exchange Value of F.Y 2020 - 2021 raised on Aug'20 | 1190260
10 | Material Exchange Value of F.Y 2020 - 2021 - raised on Nov'20 | 680250
11 | Material Exchange Value of F.Y 2020 - 2021 - raised on June'21 | 46020
12 | Material Exchange Value of F.Y 2017 -18 | 863826
13 | Miscellenous Payment | 7000000
14 | Villa no. 18 Sale Amount Adjusted agst on A/c | 8175000
| Total B | 153148953
| Net payable to contractor (A-B) | 4488604
Note : | ** UnBilled Exclusive GST Value
* Inclusive GST Value ( GST Bill Not Received )