## KNM
Prepared by: | Kavitha
Report Date | 2022-02-07
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
165601 | 19-03-2022 | Water Cooler and Carpet tiles | Po issued
165606 | 19-03-2022 | Wall fans | Cancelled-Send new requisition
165643 | 2022-05-07 | Timer machine | Po issued-89630
165680 | 21-06-2022 | Sal wood | Po to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
165599 | 19-03-2022 | Creche items | Supplier arranging material
165601 | 19-03-2022 | Rowing Machine | Supplier arranging material
165602 | 19-03-2022 | TT Table | Supplier arranging material
165609 | 19-03-2022 | Windows pleated blinds | Next week delivery
165625 | 16-04-2022 | Off white pleated blinds | Next week delivery
165629 | 23-04-2022 | Window grills | Next week delivery
165631 | 23-04-2022 | 2x2 window grills | Next week delivery
165641 | 2022-05-04 | SS stand for table | Next week delivery
165644 | 2022-05-09 | MS Gate for villa | Next week delivery
165645 | 2022-05-09 | MS Gate for villa-16 | Next week delivery
165646 | 2022-05-09 | MS Gate for villa-18 | Next week delivery
165647 | 2022-05-09 | MS Gate for villa-42 | Next week delivery
165648 | 2022-05-09 | MS Gate for villa-52 | Next week delivery
165649 | 2022-05-09 | MS Gate for villa-65 | Next week delivery
165650 | 2022-11-05 | Window grills | Next week delivery
165661 | 25-05-2022 | MS Round pipe | Next week delivery
165662 | 26-05-2022 | Yoga mat | Next week delivery
165663 | 26-06-2022 | Twindle GO-round | Next week delivery
165664 | 26-05-2022 | Garbage cover | Next week delivery
165665 | 27-05-2022 | Regal beige-4x2 | Next week delivery
165677 | 2022-07-06 | SS Railing | Next week delivery
165678 | 2022-07-06 | SS Railing | Next week delivery