## KNM
Prepared by: | Kavitha
Report Date | 20-06-2022
Site | MRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
95122 | 2022-05-04 | Cafeterial material | Coffee machine admin to follow up, Double door fridge po issud
95131 | 14-05-2022 | CPVC Material | PO Issued-po no-88339
95140 | 28-05-2022 | vinyle flooring | po to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
95085 | 16-03-2022 | Recreation Room | contact supplier
95087 | 16-03-2022 | RO Plant | Supplier arranging Material
95122 | 2022-04-05 | Chairs | Supplier arranging Material
95132 | 19-05-2022 | Hallow bricks | Supplier arranging Material
95135 | 25-05-2022 | Split AC | Supplier arranging Material
95136 | 25-05-2022 | Floor mat | Supplier arranging Material
95137 | 25-05-2022 | Victory chairs | contact supplier
95138 | 28-05-2022 | Hallow bricks | Supplier arranging Material
95141 | 30-05-2022 | JBL | Pick up from SSLLP
94149 | 2022-03-06 | Pendrive | Pick up from SSLLP
95151 | 2022-06-06 | Carpet tiles | contact supplier
95153 | 2022-07-06 | Tanbrown granite | Pick up from SOV
95154 | 2022-08-06 | Plywood | contact supplier
95157 | 16-06-22 | CC Bonding agent | Pick up from SSLLP