## Vista
Prepared by: | vanajakshi
Report Date | 06.07.2022
Site | Vista Homes
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
180935 | 30.06.2022 | cement bags | PO to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
180934 | 27.06.2022 | CP Material | Deliver by tomorrow