## VOC LLP
Prepared by: | Mounika
Report Date | 02.07.22
Site | Nxetopolis
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186348 | 28.06.22 | Laptop Bag | On linePurchase
186347 | 28.06.22 | Bio-Metric Battery | On linePurchase
186346 | 28.06.22 | MCB-16 amps | Po to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
186330 | 06.06.22 | MS Stool | This week delivary
186312 | 14.05.22 | Nylon Cricket net | This week delivary