## NE
Prepared by: | Mounika
Report Date | 02.07.22
Site | Nilgiri Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
182023 | 29.06.22 | Safety shoe | 89683 & 89684
182022 | 28.06.22 | Curing pipe | 89685
182016 | 20.06.22 | MS Z angle | Po to be issue
181987 | 31.05.22 | Flat Files | 88776
List of requisitions Where PO/WO is prepared and items have not received at site
181941 | 06.05.22 | MI Video Camera | This week delivary
181979 | 25.05.22 | Roller Blinds | This week delivary
182005 | 09.06.22 | Al Fixied Windows | Monday Delivary
182015 | 20.06.22 | WPC Doors | Delivered