## Sheet1
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-07-04
Site |  | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178466 | 2022-03-29 | Digital weighing machine | PO 89500
178470 | 2022-03-29 | Sofa set | PO 87543
178544 | 2022-05-04 | Vinyl flooring | PO 88230, 89809
178598 | 2022-06-13 | Copper cloudy | PO 89687
178607 | 2022-06-17 | Wachers for parryware | PO 89673
178614 | 2022-06-24 | Flood , street lights | PO 89569
178615 | 2022-06-24 | Furniture, consumables | Wakefit purchase
178620 | 2022-06-27 | Octagnal poles | PO 89772
178622 | 2022-06-27 | Windows | PO to be issue
178623 | 2022-06-28 | Stationary | PO 89597
178624 | 2022-06-28 | Stationary and consumables | PO 89596
178625 | 2022-06-28 | Consumables | PO 89672
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
178125 | 29.10.2021 | Wall mixtures | Bulk order material is under delivery as per site requirment
178126 | 29.10.2021 | Wall mixtures | Bulk order material is under delivery as per site requirment
178127 | 29.10.2021 | Wall hung WC | Bulk order material is under delivery as per site requirment
178455 | 2022-03-26 | Creche equipments | Deliverd
178456 | 2022-03-26 | Creche equipments | Deliverd
178468 | 2022-03-29 | Playground material | Deliverd
178447 | 2022-03-31 | Toughned glass | Deliverd
178478 | 2022-04-05 | Sliding windows | Part deliverd, balance work under process
178479 | 2022-04-05 | Grills | Material under pruduction
178510 | 2022-04-16 | HOB and Chimney | Deliverd
178512 | 2022-04-16 | Glass partition | Work under process
178522 | 2022-04-23 | Wood dark | Pick up from SSLLP-GMR
178551 | 2022-05-09 | Tiles | Pick up from SSLLP-GMR
178457 | 2022-05-06 | Wood dark wood | Pick up from ssllp-gmr
178568 | 2022-05-25 | Kitchen unit | Deliverd
178578 | 2022-05-31 | Panel doors | Pick up from SSLLP.
178609 | 2022-06-21 | Door matt | Deliverd
178608 | 2022-06-21 | Router | Pick up from ssllp
178606 | 2022-06-15 | CPVC | Deliverd
178602 | 2022-06-15 | Consumables items | Deliverd
178600 | 2022-06-15 | Consumables items | Deliverd
178595 | 2022-06-13 | Granite | Deliverd
178594 | 2022-06-11 | Granite | Pick up from SSLLP-SOVLLP
178592 | 2022-06-11 | UPVC | Material under production
178618 | 2022-06-24 | Wall, floor tiles | Pick up from SSLLP-GMR
178617 | 2022-06-24 | Wall, floor tiles | Pick up from SSLLP-GMR
178616 | 2022-06-24 | Floor tiles | Pick up from SSLLP-GMR