## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-07-02
Site |  | GVRC
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
206003 | 2022-06-04 | Laptop | Hold by sunil
206004 | 2022-06-03 | MEP Tools | Awaiting for quotes
206005 | 2022-06-03 | Cutting plair, nose player, screw driver etc., | PO 89421, 89631, 89830
206006 | 2022-06-03 | Tool box, lock, pipe, wrinch, monkey spaner etc., | PO 89624
206007 | 2022-06-06 | Server PC | PO 89833
206020 | 2022-06-14 | D Link router | PO 89801
206023 | 2022-06-14 | Table with low storage unit, low storages | PO 89549
206024 | 2022-06-14 | 4 Core armourd cable, service wire, MCB, DB | PO 89723, 89724
206027 | 2022-06-15 | MS Sheet grey colour | PO 89426, 89427
206032 | 2022-06-16 | MS Poder coated kerbee sheets | PO to be issue
206034 | 2022-06-18 | Flush doors | PO 89768
206036 | 2022-06-17 | MS Rolling shutter | PO to be issue
206044 | 2022-06-21 | SS Riling | This requisition has been cancelled, due to qty mistake and raised another requisition no 206076, PO 89756, You can cancel this requisition
206047 | 2022-06-23 | Sypone pipe, threaded dummy, teflon tapes, air vent | PO 89402, 89686, 89689
206054 | 2022-06-25 | LED Tube light | PO 89572
206055 | 2022-06-27 | Anchor bolts | PO 89637
206057 | 2022-06-29 | Janthapaste, araldite and adhesives | PO 89601
206058 | 2022-06-29 | Sponges, coconut broomsm bombay brooms | PO 89603
206059 | 2022-06-29 | Spike buster | PO 89731
206061 | 2022-06-29 | Electrical items | PO 89642
206062 | 2022-06-29 | RMC | PO 89576
206063 | 2022-06-30 | MS Gazzette plates | Local purchase and deliverd to site close this requisition
206064 | 2022-06-30 | Curb stone | PO 89625
206065 | 2022-06-30 | Anchor bolts | PO 89635
206066 | 2022-06-30 | Carpet grass | PO 89674
List of requisitions Where PO/WO is prepared and items have not received at site
163704 | 2021-08-07 | ACP cladding | Work under progress
164829 | 2022-04-09 | Cera board | Work under process by karunakar,clarification required from madhu to karunakar
164851 | 2022-04-14 | Bathroom door | No response from supplier will get back to you once we speak to supplier
164894 | 2022-04-23 | FRD Doors | Deliverd
164920 | 2022-05-06 | PU Foam | Pick up from Supplier place
164923 | 2022-05-05 | Luminious inverter battary | Deliverd
164929 | 2022-05-06 | ACP cladding | Work under process Pinnaccle
164923 | 2022-05-11 | ACP Walls pop work | Deliverd
164987 | 2022-05-27 | Galvalume sheet | Pick up from Supplier place
164993 | 2022-05-30 | JBL CSL | Deliverd
206014 | 2022-06-13 | Steel grey granite | Pick up from SOVLLP
206021 | 2022-06-14 | Fire extiunguisher | Pick up from Kothari
206025 | 2022-06-15 | Arm grout inject | Pick up from Anisha
206026 | 2022-06-15 | Steel grey granite | Pick up from SOVLLP
206037 | 2022-06-17 | Adhesive chemical | Pick up from Anisha
206014 | 2022-06-13 | Steel grey granite | Pick up from SSLLP-SOVLLP
206025 | 2022-06-15 | Arm grout inject, PU 1, Floarm tool clean | Pick up from Supplier place
206026 | 2022-06-15 | Steel grey granite | Pick up from SSLLP-SOVLLP
206040 | 2022-06-17 | Cutting blades | Pick up from Supplier place
206046 | 2022-06-23 | Curb stone | Co ordinate with supplier for delivery