## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-07-09
Site |  | GVRC
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
206003 | 2022-06-04 | Laptop | PO 90124
206004 | 2022-06-03 | MEP Tools | PO 90125
206024 | 2022-06-14 | 4 Core armourd cable, service wire, MCB, DB | PO 89723, 89724, 89969
206032 | 2022-06-16 | MS Poder coated kerbee sheets | PO 90130
206036 | 2022-06-17 | MS Rolling shutter | PO to be issue
206063 | 2022-06-30 | MS Gazzette plates | Local purchase and deliverd to site close this requisition
206068 | 2022-07-01 | Aluminium lugs | PO89970
206070 | 2022-07-01 | Al cable, LED Lights | PO 90009, 90033
206073 | 2022-06-04 | Cement bags | PO Not found in email send it again
206082 | 2022-07-06 | Coffee powder | PO to be issue
206086 | 2022-07-07 | Galvanized roofing sheets | PO to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
163704 | 2021-08-07 | ACP cladding | Work under progress
164829 | 2022-04-09 | Cera board | Work under process by karunakar,clarification required from madhu to karunakar
164851 | 2022-04-14 | Bathroom door | Close this no response from supplier and raise another requisition if required
164894 | 2022-04-23 | FRD Doors | Deliverd
164920 | 2022-05-06 | PU Foam | Pick up from Supplier place
164929 | 2022-05-06 | ACP cladding | Work under process Pinnaccle
164923 | 2022-05-11 | ACP Walls pop work | Deliverd
164987 | 2022-05-27 | Galvalume sheet | Pick up from Supplier place
206005 | 2022-06-03 | Cutting plair, nose plair, screw drivers etc., | Pick up from Supplier place
206006 | 2022-06-03 | Tool box, lock, pipe wrinch etc., | Pick up from Supplier place
206014 | 2022-06-13 | Steel grey granite | Pick up from SOVLLP
206026 | 2022-06-15 | Steel grey granite | Pick up from SOVLLP
206034 | 2022-06-18 | Flush doors | Next delivery by supplier
206046 | 2022-06-23 | Curb stone | Deliverd
206066 | 2022-06-30 | Carpet grass | As per requirment supplier will deliver
206067 | 2022-06-30 | Galvalume sheet | Cancelled by site
206074 | 2022-07-05 | Online ph meter | Deliverd
206075 | 2022-07-05 | Weighing machine | Deliverd
206076 | 2022-07-05 | SS Railing | Work under process
206077 | 2022-07-06 | Cera board | Work under process
206083 | 2022-07-06 | Weiding rods | Deliverd
206087 | 2022-07-07 | LED Flood lights | Deliverd