## Vista
Prepared by: | vanajakshi
Report Date | 22.07.2022
Site | Serene Farms
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
150642 | 22.06.2022 | Rain coats and umbrella | stock available at SSLLP.Deliver by next week,waiting for vehicle arrangement
150641 | 22.06.2022 | CP and Sanitary | stock available at SSLLP.Deliver by next week,waiting for vehicle arrangement
150640 | 22.06.2022 | CP and Sanitary | stock available at SSLLP.Deliver by next week,waiting for vehicle arrangement
150643 | 9.07.202 | CP and Sanitary | stock available at SSLLP.Deliver by next week,waiting for vehicle arrangement
150644 | 9.07.2022 | CP and Sanitary | stock available at SSLLP.Deliver by next week,waiting for vehicle arrangement