## Sheet1
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-07-09
Site |  | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178470 | 2022-03-29 | Sofa set | Cancelled by Site
178544 | 2022-05-04 | Vinyl flooring | PO 88230, 89809
178615 | 2022-06-24 | Furniture, consumables | Wakefit purchase, COD
178620 | 2022-06-27 | Octagnal poles | PO 89772
178622 | 2022-06-27 | Windows | PO 90252
178628 | 2022-07-01 | Coffee table | Wakefit purchase, COD
178629 | 2022-07-06 | Floor matt | PO 89893
179615 | 2022-06-24 | Furniture, consumables | Not correct requisition check
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
178127 | 29.10.2021 | Wall hung WC | Bulk order material is under delivery as per site requirment
178455 | 2022-03-26 | Creche equipments | Deliverd
178456 | 2022-03-26 | Creche equipments | Deliverd
178469 | 2022-03-29 | Coffee tables | Searching for new vendor
178477 | 2022-03-31 | Toughned glass | Work under process
178478 | 2022-04-05 | Sliding windows | Part deliverd, balance work under process
178479 | 2022-04-05 | Grills | Material under pruduction
178510 | 2022-04-16 | HOB and Chimney | Deliverd
178512 | 2022-04-16 | Glass partition | Work under process
178522 | 2022-04-23 | Wood dark | Awaiting to receive the stock from supplier.
178547 | 2022-05-06 | Wood dark wood | Deliverd
178551 | 2022-05-09 | Tiles dark wood | Deliverd
178568 | 2022-05-25 | Kitchen Unit | The material got damaged so they are making again expecting delivery in August 1st week
178578 | 2022-05-31 | Panel doors | Deliverd
178592 | 2022-06-11 | UPVC | Part deliverd, balance work under process
178594 | 2022-06-11 | Granite Tan brown | Pick up from SSLLP-SOVLLP
178595 | 2022-06-13 | Granite Tan brown | Pick up from SSLLP-SOVLLP
178600 | 2022-06-15 | Consumables wall putty | Deliverd
178602 | 2022-06-15 | Consumables items | Deliverd
178606 | 2022-06-15 | CPVC | Deliverd
178608 | 2022-06-21 | Router | Monday delivery
178617 | 2022-06-24 | Wall tiles | Part deliverd, balance awaiting to receive from supplier
178623 | 2022-06-28 | Pens | Deliverd
178624 | 2022-06-28 | Coffee powder | Cancel this and raise the new requisition