## KNM
Prepared by: | Kavitha
Report Date | 13-07-2022
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
165601 | 19-03-2022 | Carpet Tiles | Po issued
165606 | 19-03-2022 | Wall fans | Cancelled-Send new requisition
165683 | 27-06-2022 | Simply go around | Po issued-89890
165684 | 27-06-2022 | RO Plant servicing | Sent to MDs approval
165685 | 30-06-2022 | MS Railing | Po to be issue
165687 | 2022-07-06 | AL Sl windows | Po to be issue
165688 | 2022-07-06 | MS Window grills | Po to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
165599 | 19-03-2022 | Creche items | Supplier arranging material
165602 | 19-03-2022 | TT Table | Supplier arranging material
165629 | 23-04-2022 | Window grills | Next week delivery
165631 | 23-04-2022 | 2x2 window grills | Next week delivery
165641 | 2022-05-04 | SS stand for table | Next week delivery
165643 | 2022-05-07 | Timer machine | Next week delivery
165644 | 2022-05-09 | MS Gate for villa | Next week delivery
165645 | 2022-05-09 | MS Gate for villa-16 | Next week delivery
165646 | 2022-05-09 | MS Gate for villa-18 | Next week delivery
165647 | 2022-05-09 | MS Gate for villa-42 | Next week delivery
165648 | 2022-05-09 | MS Gate for villa-52 | Next week delivery
165649 | 2022-05-09 | MS Gate for villa-65 | Next week delivery
165650 | 2022-11-05 | Window grills | Next week delivery
165662 | 26-05-2022 | Yoga mat | Next week delivery
165664 | 26-05-2022 | Garbage cover | Next week delivery
165680 | 21-6-2022 | Sal wood | Next week delivery