## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-07-16
Site |  | GVRC
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
206003 | 2022-06-04 | Laptop | PO 90124
206004 | 2022-06-03 | MEP Tools | PO 90125
206024 | 2022-06-14 | Timer with contactor,flex tape | PO 90428
206032 | 2022-06-16 | MS Poder coated kerbee sheets | PO 90130
206036 | 2022-06-17 | MS Rolling shutter | PO 90728
206047 | 2022-06-23 | MS Socket | PO 89686, 89869
206068 | 2022-07-07 | Cable tray | PO 89970
206070 | 2022-07-01 | Al cable, LED Lights | PO 90009, 90033
206086 | 2022-07-07 | Galvanised roofing sheet | PO 90173
206091 | 2022-07-12 | 2 sq mm single core copper, service wire | PO to be issue
206094 | 2022-07-12 | Aluminium cladding rook wool | Cancelled as per Akhi, on MD instructions
206100 | 2022-07-14 | MS Gezzatte plate | Local purchase by Raghu
List of requisitions Where PO/WO is prepared and items have not received at site
164829 | 2022-04-09 | Cera board | Work under process by karunakar,clarification required from madhu to karunakar
164851 | 2022-04-14 | Bathroom door | Close this no response from supplier and raise another requisition if required
164894 | 2022-04-23 | FRD Doors | Deliverd, installation supplier will do co ordinate with him
164920 | 2022-05-06 | PU Foam | Cancel this and put a new requisition
164929 | 2022-05-06 | ACP cladding | Work under process Pinnaccle
164987 | 2022-05-27 | Galvalume sheet | Pick up from Supplier place
206014 | 2022-06-13 | Steel grey granite | Pick up from SOVLLP
206026 | 2022-06-15 | Steel grey granite | Pick up from SOVLLP
206034 | 2022-06-18 | Flush doors | Deliverd
206066 | 2022-06-30 | Carpet grass | As per requirment supplier will deliver
206067 | 2022-06-30 | Galvalume sheet | Cancelled by site
206076 | 2022-07-05 | SS Railing | Work under process
206077 | 2022-07-06 | Cera board | Work under process
206087 | 2022-07-07 | LED Flood lights | Deliverd