## Vista
Prepared by:Ramya | Ramya
Report Date | 27.07.22
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
165601 | 19.03.22 | Carpet tiles for gym | PO issued-po no 90006
165685 | 30-06-22 | MS Railing | po to be issue
165688 | 2022-06-07 | MS Grill | po to be issue
165689 | 2022-12-07 | SI.A1 Window 6*4 | po to be issue
165691 | 15-07-22 | SS Name plates | po to be issue
165692 | 15-07-22 | CP Jali | po to be issue
165697 | 22-07-22 | CP Fitting items | PO issued-po no 90328,30332
165698 | 22-07-22 | Sanitary items | PO issued-po no 90336
165699 | 22-07-22 | Copper plates | PO issued-po no 90394
165700 | 22-07-22 | Wires materials | PO issued-po no 90392
List of requisitions Where PO/WO is prepared and items have not been received at site beyond the lead time:
165602 | 19.03.22 | TT table | Delivery by this week
165629 | 23-04-22 | Windows Grills | Delivery by this week
165631 | 23-04-22 | Windows Grills | Delivery by this week
165641 | 2022-04-05 | SS stand for table | Delivery by this week
165643 | 2022-07-05 | Timer machines | Follow up with supplier
165644 | 2022-09-05 | MS gate for villa | Delivery by this week
165645 | 2022-09-05 | MS gate for v. no16 | Delivery by this week
165646 | 2022-09-05 | MS gate for v. no18 | Delivery by this week
165647 | 2022-09-05 | MS gate for v. no42 | Delivery by this week
165648 | 2022-09-05 | MS gate for v. no52 | Delivery by this week
165649 | 2022-09-05 | MS gate for v. no65 | Delivery by this week
165662 | 26-05-22 | Yoga mat | Follow up with supplier
165664 | 26-05-22 | Garbage bin | Follow up with supplier
165680 | 21-06-22 | Sal wood | pick up from ssllp
165683 | 27.06.22 | Simply go ground | Follow up with supplier
165690 | 15-07-22 | Toy items | Delivery by this week
16569 | 15-07-22 | Switches v. no 81 | pick up from ssllp
165694 | 15-07-22 | Switches v. no 82 | pick up from ssllp
165695 | 15-07-22 | Altek- wall putty | pick up from ssllp
165696 | 19.07.22 | Rain coat | pick up from ssllp