## Vista
Prepared by: | vanajakshi
Report Date | 28.07.2022
Site | Vista Homes
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
|  | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
180937 | 18.07.2022 | CC Cameras | Stock available at SSLLP.Deliver by tomorrow or day afetr tomorrow
180938 | 25.07.2022 | CP Material | Stock available at SSLLP.Deliver by tomorrow or day afetr tomorrow
180939 | 25.07.2022 | Sanitary material | Stock available at SSLLP.Deliver by tomorrow or day afetr tomorrow
180940 | 25.07.2022 | cement,janatha paste | Stock available at SSLLP.Deliver by tomorrow or day afetr tomorrow