## VOC LLP
Prepared by: | Mounika
Report Date | 23.07.22
Site | Nxetopolis
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186360 | 16.07.22 | Al.Service wire | Po No- 90389 Delivered
List of requisitions Where PO/WO is prepared and items have not received at site
186312 | 14.05.22 | Nylon Cricket net | No stock at Supplier
186348 | 28.06.22 | Laptop Bags | Collect from SSLLP
186361 | 16.07.22 | Spike | Delivered
186359 | 16.07.22 | Pin Vibrator | Ready with Supplier