## Vista
Prepared by: | Ramya
Report Date | 2022-02-08
Site | SOV-part -3
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
184244 | 2022-10-06 | Aluminium windows mesh | Po to be issue
184288 | 21-06-22 | Openable windows 3 no | Po to be issue
184417 | 19-07-22 | CI Electrodes | Quotes to receive
184418 | 19-07-22 | CI Electrodes | Quotes to receive
184420 | 19-07-22 | Printer cable | Po issued-Po no-90641
184421 | 20-07-22 | Headset-JBL | Online purchase
184425 | 20-07-22 | False Ceilling | Po issued-Po no-90650
184426 | 20-07-22 | False Ceilling | Po issued-Po no-90651
184427 | 20-07-22 | False Ceilling | Po issued-Po no-90617
List of requisitions Where PO/WO is prepared and items have not received at site
184169 | 13-05-22 | Regal Beige & urbanwood dark | pick up from GMR
184171 | 13-05-22 | Carrara | pick up from GMR
184229 | 2022-01-06 | Carrara & urbanwood light | pick up from GMR
184324 | 30-06-22 | Electrical gate lamps | Follow up with supplier
184367 | 2022-02-07 | Rubber mould pavers | Follow up with supplier
184368 | 2022-02-07 | Pad locks | Follow up with supplier
184372 | 28-07-22 | Carrara,crema marfil,ultra sprinkle HL, Luna | pick up from GMR
184389 | 2022-11-07 | Wall & floor tiles | pick up from GMR
184404 | 15-07-22 | Wall & floor tiles | pick up from GMR
184405 | 15-07-22 | Wall & floor tiles | pick up from GMR
184406 | 15-07-22 | Wall & floor tiles | pick up from GMR
184408 | 18-07-22 | Vertified tiles | pick up from GMR
184409 | 18-07-22 | Wall & floor tiles | pick up from GMR
184410 | 18-07-22 | Wall & floor tiles | pick up from GMR
184411 | 18-07-22 | Wall & floor tiles | pick up from GMR
184416 | 19-07-22 | Led gate light | Follow up with supplier
184422 | 20-07-22 | WPC Door Frames | Follow up with supplier
184428 | 20-07-22 | Electrical wires | pick up from SSLLP
184429 | 20-07-22 | Electrical wires | pick up from SSLLP
184430 | 20-07-22 | Electrical wires | pick up from SSLLP
184432 | 20-07-22 | Electrical switches | pick up from SSLLP
184434 | 20-07-22 | WPC Door Frames | Follow up with supplier
184435 | 20-07-22 | WPC Door Frames | Follow up with supplier
184436 | 21-07-22 | Electrical switches | pick up from SSLLP
184439 | 21-07-22 | Electrical wires | pick up from SSLLP
184440 | 22-07-22 | Plumbing CP material | pick up from SSLLP
184441 | 22-07-22 | Plumbin Sanitary | pick up from SSLLP
184443 | 22-07-22 | Plumbing CP material | pick up from SSLLP
184444 | 22-07-22 | Plumbin Sanitary | pick up from SSLLP
184445 | 22-07-22 | Plumbin PVC | pick up from SSLLP