## Vista
Prepared by: | Ramya
Report Date | 2022-02-08
Site | MHPLSOV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
185259 | 26-07-22 | Pumps starter 3 phase | Deliverd
185263 | 27-07-22 | Blinds | Quotes to receive
185264 | 27-07-22 | Agro mesh | po to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
185237 | 27-06-22 | CC Hume pipes | follow up with supplier
185239 | 27-06-22 | CC Hume pipes | follow up with supplier