## Vista
Prepared by: | vanajakshi
Report Date | 03.08.2022
Site | Greenwood Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142053 | 07.07.2022 | Large tiles | Double time raised.if you want this material raise new requisition.
142061 | 11.07.2022 | Bulding material | PO Issued ,PO NO:90663
142082 | 18.07.2022 | Electrical copper wire | PO Issued ,PO NO:90232
List of requisitions Where PO/WO is prepared and items have not received at site
141278 | 16.03.2022 | Low storage | Supplier arranging material.Deliver by thursday
141349 | 05.04.2022 | glass railing | supplier arranging material
141357 | 6.04.2022 | MS Z angles | Pickup from SOV
141447 | 5.05.2022 | Coated grills | Fabrication going on
141451 | 11.05.2022 | Coated Z angles | Pickup from SOV
141888 | 24.05.2022 | Dining set with wenge chairs | Deliver by next week.
141889 | 24.05.2022 | Sofa set 2+1 | Deliver by next week
141896 | 24.05.2022 | Sofa set2+2+2+1 | Deliver by next week
141891 | 24.05.2022 | Bean bag | Deliver by next week
141898 | 24.05.2022 | Bar stool | Deliver by next week
141899 | 24.05.2022 | Nilkamal ratan furniture chairs with table set | supplier arranging material
141922 | 30.05.2022 | Cafeteria cabinates | supplier arranging material
141954 | 7.06.2022 | Router sim | Next week delivery
141955 | 9.06.2022 | Cafeteria kitchen unit | supplier arranging material
141964 | 11.06.2022 | Floor tile country almond | Pickup from GMR
142003 | 24.06.2022 | Ceramic wall tiles | Pickup from GMR
142005 | 27.06.2022 | Plumbing GI material | supplier arranging material
142014 | 28.06.2022 | MS Z angles | Fabrication going on
142015 | 28.06.2022 | MS Grills | Powder coating pending
142024 | 30.06.2022 | Crema Marfil floor tiles | Pickup from GMR
142025 | 30.06.2022 | Glass railing | supplier arranging material
142026 | 30.06.2022 | Manhole cover | Material ready collect from SSLLP
142049 | 6.07.2022 | Tan brown granite | Tuesday will be delivered
142051 | 07.07.2022 | Vertrified (Tagus & marbo opera)tiles | Pick up from GMR
142052 | 07.07.2022 | Vertrified tiles | Pick up from GMR
142056 | 07.07.2022 | Ceramic wall tiles | Pick up from GMR
142070 | 14.07.2022 | Ceramic wall tiles | Pick up from GMR