## Sheet1
Prepared by: |  | M.Mounika
Report Date |  | 30.07.22
Site |  | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178620 | 27.06.22 | Timer | Searching for new vendor
178643 | 09.07.22 | CC Cameras | Po No 90667
178651 | 14.07.22 | Wire-PVC Coated | Local Purchase
178658 | 16.07.22 | Book shelves with Glass shutter | PO 90600
178660 | 19.07.22 | CC Cameras | PO 90668
178662 | 20.07.22 | Copper Wire | Cancelled by MD Sir
178670 | 22.07.22 | Timer | Searching for new vendor
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
178127 | 29.10.2021 | Wall hung WC | Bulk order material is under delivery as per site requirment
178467 | 29.07.22 | Ice crem chiller | Delivered
178477 | 31.03.22 | Toughned glass | Work under process
178479 | 05.04.22 | Grills | Material under production
178512 | 16.04.22 | Glass partition | Work under process
178544 | 04.05.22 | Vinyl flooring | Work under process
178547 | 06.05.22 | Wood dark wood | Collect from GMR
178551 | 09.05.22 | Tiles dark wood | Collect from GMR
178654 | 16.07.22 | Squareman hole cover | This week delivary
178558 | 14.07.22 | Mulstistand wire | Collect from SSLLP
178568 | 25.05.22 | Kitchen Unit | Work under process
178578 | 31.05.22 | Panel Doors | Pick up from SSLLP.
178606 | 15.06.22 | CPVC Pipe | Pick up from SSLLP.
178594 | 11.06.22 | Tan brown Granite | Pick up from SSLLP-SOV
178608 | 21.06.2022 | Router | Monday delivery
178616 | 30.06.22 | Crema Marfil | Collect from GMR
178617 | 24.06.22 | Malasian Brown DK | Pick up from SSLLP.
178618 | 24.06.22 | Blanco tiles | Awaiting to receive the stock from supplier.
178622 | 27.06.22 | Windows | This week delivary
178633 | 06.07.22 | False ceiling | Work under process
178634 | 06.07.22 | PVC False ceiling | Work under process
178647 | 13.07.22 | Tan brown Granite | Pick up from SSLLP-SOV
178652 | 15.07.22 | SS Screws | Delivered
178653 | 16.07.22 | Book shelves with Glass shutter | Delivered
178657 | 16.07.22 | Study Tablets | Pick from Supplier
178659 | 16.07.22 | Nilkamal Chais | Pick from Supplier
178661 | 19.07.22 | Tan brown Granite | Pick up from SSLLP-SOV
178666 | 20.07.22 | Spring wire | Delivered
178671 | 23.07.22 | Internal Doors | Delivered