## Vista
Prepared by: | vanajakshi
Report Date | 09.08.2022
Site | Greenwood Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142102 | 26.07.2022 | Armored cable | Estimation sent to MD'S Approval
142111 | 1.08.2022 | Tools & cutting blade | po to be issue
142113 | 1.08.2022 | Electrical material | PO issued,PO NO:90809
142119 | 2.08.2022 | Cement ppc | Po to be issue
142117 | 2.08.2022 | Plumbing GI material | PO to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
141349 | 05.04.2022 | glass railing | supplier arranging material
141357 | 6.04.2022 | MS Z angles | Pickup from SOV
141447 | 5.05.2022 | Coated Grills | Pickup from SOV
141451 | 11.05.2022 | Coated Z angles | Pickup from SOV
141888 | 24.05.2022 | Dining set with wengw chairs | Online purchase
141889 | 24.05.2022 | Sofa set 2+1 | Online purchase
141896 | 24.05.2022 | Sofa set 2+2+2+1 | Online purchase
141922 | 30.05.2022 | Cafeteria +bar+Library cabinets | supplier arranging material
141954 | 7.06.2022 | Router sim | Today delivery
1419555 | 9.06.2022 | Cafeteria kitchen unit | supplier arranging material
141964 | 11.06.2022 | Floor tiles country almond | Pickup from GMR
142005 | 27.06.2022 | Plumbing GI material | supplier arranging material
142014 | 28.06.2022 | MS Z angles | Pickup from SOV
142015 | 28.06.2022 | MS Grills | Pickup from SOV
142025 | 30.06.2022 | glass railing | supplier arranging material
142051 | 07.07.2022 | Large tiles (Tagus & marbo opera )tiles | Pickup from GMR
142052 | 07.07.2022 | Large tiles (regal beige) | Pickup from GMR
142075 | 15.07.2022 | Creche toys & books | Next week delivery
142105 | 30.07.2022 | Plumbing GI material | supplier arranging material