## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-07-30
Site |  | GMR
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
193295 | 2022-06-06 | Visiting cards | Promitions to follw up
193465 | 2022-07-13 | Plumbing material | PO 90371,90372
193467 | 2022-07-13 | Plumbing material | PO 90370
193479 | 2022-07-14 | Electrical wires | Cancelled by MD, 90230
193485 | 2022-07-18 | Electrical wires | PO 90231
193496 | 2022-07-20 | Cannon camera | Local purchase
193498 | 2022-07-20 | Sports material, duck spring rider | Under negotiation with supplier by Procurment team
193504 | 2022-07-21 | MS Grills | PO 90656
193505 | 2022-07-21 | MS Grills | PO 90654
193508 | 2022-07-23 |  | PO 90310
193515 | 2022-07-25 | CC TV Cameras | PO 90700
List of requisitions Where PO/WO is prepared and items have not received at site
193204 | 2022-05-11 | Regal beige tiles | Deliverd
193250 | 2022-05-20 | Regal beige tiles | Deliverd
193300 | 2022-06-07 | Glass balcony railing | Part work has been done by supplier for balance work sire is not ready its seems, due to lift and other works,the supplier said
193398 | 2022-06-29 | False ceiling | Channel work already done by supplier, wiring is not done awaiting for wiring to be done.
193399 | 2022-06-29 | False ceiling | As per supplier the F 603 is completed C 402 tiles work is going on it will take time to complete after clearence from site
193406 | 2022-06-30 | Glass balcony railing | Due to site not ready the supplier awaiting, work not started yet
193407 | 2022-06-30 | False ceiling | Channel work already done by supplier, wiring is not done awaiting for wiring to be done.
193414 | 2022-07-01 | Short body | Awaiting stock to be receive from supplier, once receive will let you know
193428 | 2022-07-02 | MS Z angles | Pick up from Sov
193437 | 2022-07-07 | UPVC Windows | Deliverd
193440 | 2022-07-08 | Carrara tiles | Deliverd
193442 | 2022-07-08 | Short body | Awaiting stock to be receive from supplier, once receive will let you know
193447 | 2022-07-11 | Carrara tiles | Deliverd
193448 | 2022-07-11 | Black berry, regal beige tiles | Part deliverd balance pick up from SSLLP-GMR
193451 | 2022-07-11 | Luna LT, Luna DK | Pick up from SSLLP-GMR
193452 | 2022-07-11 | Malashiyan Br DK,LT,HL | Pick up from SSLLP-GMR
193454 | 2022-07-12 | UPVC Ventilator | Work under process
193461 | 2022-07-12 | Short body | Deliverd
193463 | 2022-07-13 | Tan brown granite | Deliverd
193464 | 2022-07-15 | Roff stone tile adhesive | Deliverd
193469 | 2022-07-13 | Tan brown granite | Deliverd
193470 | 2022-07-13 | Plumbing GI Pipe B class | Deliverd
193471 | 2022-07-13 | Plumbing GI Pipe B class | Deliverd