## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-08-06
Site |  | GMR
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Missing requisitions
193215 |  | PVC Material | PO 90722
193275 |  | Tiles | Req cancelled due to old format, send the req in new SKU Format
193318 |  | MS Flat | PO to be issue
193356 |  | Plumbing material | PO 90932
193563 |  | Siren | PO 90931
List of requisitions Where PO/WO not prepared 3 working days after requisition:
193295 | 2022-06-06 | Visiting cards | Promitions to follw up
193465 | 2022-07-13 | Plumbing material | PO 90371,90372
193467 | 2022-07-13 | Plumbing material | PO 90370
193496 | 2022-07-20 | Camera- Cannon | Local purchase
193485 | 2022-07-18 | Electrical wires | PO 90231
193496 | 2022-07-20 | Cannon camera | Local purchase
193527 | 2022-07-27 | Laptop bag, laptop | PO 90947
193536 | 2022-07-28 | Plumbing material | PO 90845
193546 | 2022-07-30 | Plumbing material, Fire safety material | Quotes to be receive from supplier
193508 | 2022-07-23 | Electrical wires | PO 90310
193515 | 2022-07-25 | CC TV Cameras | PO 90700
193566 | 2022-08-03 | Vitrified tiles | PO 90765
193567 | 2022-08-03 | Reflector | PO to be issue
193568 | 2022-08-03 | CP Material | PO 90752
193569 | 2022-08-03 | CP Material | PO 90753
193570 | 2022-08-03 | GI U clamp | PO 90860, 90875
List of requisitions Where PO/WO is prepared and items have not received at site
193204 | 2022-05-11 | Regal beige tiles | Deliverd
193250 | 2022-05-20 | Regal beige tiles | Awaiting stock to be receive from supplier, once receive will let you know
193218 | 2022-05-16 | Pressure switch | Pick up from supplier, already spoke to supplier
193300 | 2022-06-07 | Glass balcony railing | Part work has been done by supplier for balance work sire is not ready its seems, due to lift and other works,the supplier said
193398 | 2022-06-29 | False ceiling | Channel work already done by supplier, wiring is not done awaiting for wiring to be done.
193399 | 2022-06-29 | False ceiling | As per supplier the F 603 is completed C 402 tiles work is going on it will take time to complete after clearence from site
193406 | 2022-06-30 | Glass balcony railing | Due to site not ready the supplier awaiting, work not started yet
193407 | 2022-06-30 | False ceiling | Channel work already done by supplier, wiring is not done awaiting for wiring to be done.
193400 | 2022-06-29 | Door beeding | Deliverd
193414 | 2022-07-01 | Short body | Awaiting stock to be receive from supplier, once receive will let you know
193428 | 2022-07-02 | MS Z angles | Pick up from Sov
193437 | 2022-07-07 | UPVC Windows | Deliverd
193440 | 2022-07-08 | Carrara tiles | Deliverd
193442 | 2022-07-08 | Short body | Awaiting stock to be receive from supplier, once receive will let you know
193447 | 2022-07-11 | Carrara tiles | Deliverd
193448 | 2022-07-11 | Black berry, regal beige tiles | Part deliverd balance pick up from SSLLP-GMR
193451 | 2022-07-11 | Luna LT, Luna DK | Pick up from SSLLP-GMR
193452 | 2022-07-11 | Malashiyan Br DK,LT,HL | Pick up from SSLLP-GMR
193454 | 2022-07-12 | UPVC Ventilator | Work under process
193461 | 2022-07-12 | Short body | Deliverd
193463 | 2022-07-13 | Tan brown granite | Deliverd
193464 | 2022-07-15 | Roff stone tile adhesive | Deliverd
193465 | 2022-07-13 | Plumbing material | Deliverd
193467 | 2022-07-13 | Plumbing material | Deliverd
193469 | 2022-07-13 | Tan brown granite | Deliverd
193470 | 2022-07-13 | Plumbing GI Pipe B class | Deliverd
193471 | 2022-07-13 | Plumbing GI Pipe B class | Deliverd
193473 | 2022-07-13 | CPVC Material | Deliverd
193504 | 2022-07-21 | MS Grills | Under poder coating will be delivered in 4-5 days
193505 | 2022-07-21 | MS Grills | Under poder coating will be delivered in 4-5 days
193513 | 2022-07-25 | Panel doors | Pick up from SSLLP.
193514 | 2022-07-25 | Granite, general material | Deliverd
193529 | 2022-07-27 | MS Round pipe, MS Flat, L angle | Deliverd
193532 | 2022-07-28 | UPVC Windows | Under fabrication
193533 | 2022-07-28 | Floor paint | Deliverd
193534 | 2022-07-28 | MS Langle, MS Flat, Flat patti | Deliverd
193535 | 2022-07-28 | Electrical material | Deliverd
193537 | 2022-07-29 | Labour helmets | Deliverd
193538 | 2022-07-29 | Square manhole | Deliverd
193540 | 2022-07-29 | Electrical material | Deliverd
193541 | 2022-07-29 | Interlocking pavers | Co ordinate with supplier for delivery
193542 | 2022-07-30 | MS Material | Pick up from supplier, already spoke to supplier
193543 | 2022-07-30 | SS name plate | Monday delivery by supplier
193545 | 2022-07-30 | Hardware material | Pick up from supplier, already spoke to supplier