## Vista
Prepared by: | Ramya
Report Date | 2022-13-08
Site | SOV-part -3
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
184417 | 19-07-22 | CI Electrodes | Po issued-Po no-90922
184418 | 19-07-22 | CI Electrodes | Po issued-Po no-90921
184421 | 20-07-22 | Headset-JBL | Quotes to receive
184469 | 2022-03-08 | Electrical conducting material | Po issued-Po no-90774
184470 | 2022-03-08 | Electrical conducting material | Po issued-Po no-90797
184471 | 2022-03-08 | Electrical conducting material | Po issued-Po no-90777
184472 | 2022-03-08 | Electrical conducting material | Po issued-Po no-90783
184473 | 2022-03-08 | Vertified tiles Biblios | Po issued-Po no-90767
List of requisitions Where PO/WO is prepared and items have not received at site
184169 | 13-05-22 | Regal Beige & urbanwood dark | pick up from GMR
184171 | 13-05-22 | Carrara | pick up from GMR
184229 | 2022-01-06 | Carrara & urbanwood light | pick up from GMR
184367 | 30-06-22 | Rubber mould pavers | Follow up with supplier
184368 | 2022-02-07 | pad locks | delivery by this week
184372 | 2022-02-07 | Carrara,crema marfil,ultra sprinkle HL, Luna | pick up from GMR
184389 | 2022-02-07 | Wall & floor tiles | pick up from GMR
184404 | 28-07-22 | Wall & floor tiles | pick up from GMR
184405 | 2022-11-07 | Wall & floor tiles | pick up from GMR
184406 | 15-07-22 | Wall & floor tiles | pick up from GMR
184408 | 15-07-22 | Vertified tiles | pick up from GMR
184409 | 15-07-22 | Wall & floor tiles | pick up from GMR
184410 | 18-07-22 | Wall & floor tiles | pick up from GMR
184416 | 18-07-22 | Led gate light | Follow up with supplier
184420 | 18-07-22 | printer cable | pick up from SSLLP
184422 | 18-07-22 | WPC Door Frames | Follow up with supplier
184432 | 19-07-22 | Electrical switches | pick up from SSLLP
184441 | 20-07-22 | plumbing Sanitary | pick up from SSLLP
184452 | 20-07-22 | Electrical switches | pick up from SSLLP
184460 | 20-07-22 | Plumbing CP material | pick up from SSLLP
184461 | 20-07-22 | plumbing Sanitary | pick up from SSLLP
184462 | 20-07-22 | Wifi cameras, router | pick up from SSLLP
184463 | 20-07-22 | Crack fill chemical | Follow up with supplier
184466 | 20-07-22 | Panel doors | deliverd
184467 | 21-07-22 | Panel doors | deliverd
184468 | 21-07-22 | Panel doors | pick up from SSLLP
184475 | 22-07-22 | Tandoor rough stone | deliverd