## NE
Prepared by: | Ramya
Report Date | 13.08.22
Site | Nilgiri Estates
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
175522 | 01.08.22 | Router | Cancelled by suneel sir
List of requisitions Where PO/WO is prepared and items have not received at site
175325 | 20.07.21 | Solar module | Legal case in MD going with this supplier
175492 | 07.03.22 | Sliding windows | Deliverd
175513 | 23.06.22 | Furniture | Supplier arranging material
175515 | 2022-07-07 | Sliding windows with mesh | Deliverd
175517 | 15.07.22 | Floor tiles | Pick up from GMR