## KNM
Prepared by: | Kavitha
Report Date | 2022-08-04
Site | DR.NRK Biotech Pvt Ltd
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186368 | 26-07-2022 | Drill machine | Po no-90610
186363 | 20-07-2022 | Mono block pump | po no-90566
List of requisitions Where PO/WO is prepared and items have not received at site
186312 | 14-05-2022 | Nylon cricket net | Follow up with supplier
186348 | 28-06-2022 | Laptop bags | Online purchase
186359 | 16-07-2022 | Pin vibrator | Pick up from supplier