## KNM
Prepared by: | Kavitha
Report Date | 2021-08-11
Site | DR.NRK Biotech Pvt Ltd
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186376 | 2022-08-03 | Door frames with thresholf | PO Issued, Po no-90814
List of requisitions Where PO/WO is prepared and items have not received at site
186312 | 14-05-2022 | Nylon cricket net | Follow up with supplier
186348 | 28-06-2022 | Laptop bags | Online purchase
186359 | 16-07-2022 | Pin vibrator | Pick up from supplier
186373 | 2022-08-02 | Recron | Pick up from SSLLP