## KNM
Prepared by: | Kavitha
Report Date | 28-07-2022
Site | Vista Homes
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
180937 | 18-07-2022 | CC Cemeras | Pick up from SSLLP
180938 | 25-07-2022 | CP Material | Pick up from SSLLP
180939 | 25-07-2022 | Sanitary material | Pick up from SSLLP
180940 | 25-07-2022 | Cement, Jantha paste | Pick up from SSLLP