## Vista
Prepared by: | vanajakshi
Report Date | 17.08.2022
Site | Greenwood Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142102 | 26.07.2022 | Armored cable | Duplicate sent to MD'S Approval
142117 | 2.08.2022 | Plumbing GI material | Rates to confirm by Anand sir
142137 | 09.08.2022 | Anchor bolt,threaded rod | Po to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
141357 | 6.04.2022 | MS Z angles | Pickup from SOV
141451 | 11.05.2022 | Coated Z angles | Pickup from SOV
141447 | 5.05.2022 | Coated Grills | Pickup from SOV
141889 | 24.05.2022 | Sofa set 2+1 | Today delivery
141896 | 24.05.2022 | Sofa set 2+2+2+1 | Delivered
141922 | 30.05.2022 | Cafeteria +bar+Library cabinets | Today delivery
141954 | 7.06.2022 | Router sim | Delivered
1419555 | 9.06.2022 | Cafeteria kitchen unit | Today delivery
141964 | 11.06.2022 | Floor tiles country almond | Pickup from GMR
142014 | 28.06.2022 | MS Z angles | Pickup from SOV
142015 | 28.06.2022 | MS Grills | Pickup from SOV
142051 | 07.07.2022 | Large tiles (Tagus & marbo opera )tiles | Pickup from GMR
142052 | 07.07.2022 | Large tiles (regal beige) | Pickup from GMR
142075 | 15.07.2022 | Creche toys & books | Next week delivery
142087 | 20.07.2022 | Taugs & Marbo-opera tiles | Pickup from GMR
142090 | 21.07.2022 | Plywood | Delivered
142107 | 30.07.2022 | CP sink cock | Next week delivery
142110 | 01.08.2022 | CC Hume pipe | supplier arranging material
142111 | 01.08.2022 | Cutting blade | supplier arranging material
142115 | 02.08.2022 | Guard alert siren | supplier arranging material
142118 | 02.08.2022 | Paints | Delivered
142121 | 03.08.2022 | Regal Beige &Urbanwood dark tiles | Pickup from GMR