## Vista
Prepared by: | vanajakshi
Report Date | 17.08.2022
Site | Kadakia & Modi Housing
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
|  | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
21703 | 30.07.2022 | Armoured cable | Supplier arranging material