## KNM
Prepared by: | Deepa
Report Date | 18.08.22
Site | MRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
95165 | 04.07.22 | MS Z angle | Next weak will be deliverd
95171 | 15.07.22 | CI electrode,chemical earthing | Follow up with suppleir
95172 | 15.07.22 | push & go crawling toy Next weak will be delivered | Next weak will be deliverd
95177 | 28.07.22 | Door Salwood | pick up from ssllp
95180 | 01.08.22 | Delivery challan book | Promotions to follow up
95181 | 02.08.22 | Guard alert siren | Next weak will be deliverd
95182 | 04.08.22 | safety material | Next weak will be deliverd
95185 | 08.08.22 | Electrical material | pick up from ssllp
95186 | 12.08.22 | Hollow bricks | Follow up with suppleir
95187 | 12.08.22 | Hollow bricks | Follow up with suppleir