## KNM
Prepared by: | Deepa
Report Date | 13.08.2022
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
165629 | 23-04-2022 | Window grills | Next week delivery
165631 | 23-04-2022 | 2x2 window grills | Next week delivery
165643 | 2022-05-07 | Timer machine | Next week delivery
165645 | 2022-05-09 | MS Gate for villa-16 | Next week delivery
165646 | 2022-05-09 | MS Gate for villa-18 | Next week delivery
165664 | 26-05-2022 | Garbage bin | Next week delivery
165688 | 06.07.22 | MS grill | Next week delivery
165689 | 12.07.22 | S1 .A1.window 6 x 4 only | Next week delivery
165690 | 15.07.22 | Toys and books | Next week delivery
165691 | 15.07.22 | SS name plates | Next week delivery
165697 | 22.07.22 | Wall mixture | Next week delivery
165701 | 02.08.22 | Guard alert siren | Next week delivery
165703 | 06.08.22 | Tiles grouting | Next week delivery
165704 | 06.08.22 | Electrical Wires | Next week delivery