## Vista
Prepared by: | Ramya
Report Date | 2022-19-08
Site | SOV-part -3
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
184421 | 20-07-22 | Headset-JBL | Sunday Delivery
184483 | 2022-06-08 | GI wire pvc coated | Searching in market
184484 | 2022-08-08 | Vertified nitco biblios | Po issued-Po no-91026
184488 | 2022-10-08 | Router sim based TP-link | Po issued-Po no-91030 | Material delivered
List of requisitions Where PO/WO is prepared and items have not received at site
184169 | 13-05-22 | Regal Beige & urbanwood dark | pick up from GMR
184171 | 13-05-22 | Carrara | pick up from GMR
184324 | 30-06-22 | Led gate light | cancelled
184367 | 2022-02-07 | Rubber mould pavers | Follow up with supplier
184368 | 2022-02-07 | Pad locks | delivery by this week
184372 | 28-07-22 | Ultra Sprinkle HL, luna DK | deliverd
184389 | 2022-11-07 | Wall & floor tiles almond 40 boxes | pick up from GMR
184404 | 15-07-22 | Wall & floor tiles | pick up from GMR
184405 | 15-07-22 | Wall & floor tiles | pick up from GMR
184406 | 15-07-22 | Wall & floor tiles | pick up from GMR
184408 | 18-07-22 | Vertified tiles | pick up from GMR
184409 | 18-07-22 | Wall & floor tiles | pick up from GMR
184410 | 18-07-22 | Wall & floor tiles | pick up from GMR
184411 | 18-07-22 | Urbanwood natural | pick up from GMR
184416 | 19-07-22 | Led gate light | deliverd
184417 | 19-07-22 | CI Electrodes | deliverd
184418 | 19-07-22 | CI Electrodes | deliverd
184420 | 19-07-22 | printer cable | pick up from SSLLP
184422 | 20-07-22 | WPC Door Frames | pick up from SSLLP
184432 | 20-07-22 | Electrical switches | deliverd
184434 | 20-07-22 | WPC Door Frames | pick up from SSLLP
184452 | 27-07-22 | Electrical switches | deliverd
184460 | 29-07-22 | Plumbing CP material | pick up from SSLLP
184461 | 29-07-22 | plumbing Sanitary | pick up from SSLLP
184462 | 30-07-22 | Wifi cameras | deliverd
184463 | 2022-01-08 | Crack fill chemical | pick up from SSLLP
184468 | 2022-03-08 | panel main doors & SS hinges | pick up from SSLLP
184473 | 2022-03-08 | V.tiles nitco biblios | pick up from GMR
184476 | 2022-04-08 | UPVC openable windows | Follow up with supplier
184477 | 2022-04-08 | UPVC Window Sliding mesh | Follow up with supplier
184479 | 2022-05-08 | Plumbing CP material | pick up from SSLLP
184480 | 05-08-022 | plumbing Sanitary | pick up from SSLLP
184482 | 2022-05-08 | Electrical material | pick up from SSLLP
184485 | 2022-08-08 | nitco wall & floor tiles | pick up from SSLLP
184487 | 2022-09-08 | UPVC Windows | Follow up with supplier
184489 | 2022-10-08 | Electrical wires | pick up from SSLLP