## KNM
Prepared by: | Mounika
Report Date | 2022-08-16
Site | NGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
182043 | 14.07.22 | Timer | Serching for Vendor
182083 | 03.08.22 | PVC Injuction Nozzle | Local Purchase
List of requisitions Where PO/WO is prepared and items have not received at site
182061 | 25.07.221 | Proportion Box | Monday Delivary
182066 | 26.07.22 | Z -Angle | Pick from SSLLP
182067 | 26.07.22 | Door Frames | Pick from SSLLP
182078 | 01.08.22 | Blue sheet | Pick from SSLLP
182079 | 02.08.22 | Guard Alert | Pick from Supplier
182085 | 04.08.22 | MS Shelves | Pick from SSLLP
182088 | 04.08.22 | HDPE Tank | Pick from SSLLP
182095 | 06.08.22 | Anchort bolt | Pick from SSLLP
182098 | 06.08.22 | Furniture | Pick from SSLLP
182099 | 06.08.22 | Tan Brown Granite | Pick from SSLLP
182101 | 08.08.22 | Flush oors | Pick from Supplier
182102 | 08.08.22 | Electrical wires | Pick from SSLLP
182103 | 08.08.22 | Bentonite Powder | Pick from SSLLP
182104 | 09.08.22 | Consumables | Pick from SSLLP
182105 | 09.08.22 | Chemical RO Plant | Pick from Supplier
182106 | 09.08.22 | CPVC Material | Pick from SSLLP
182107 | 09.08.22 | LED Tube Light | Pick from SSLLP
182108 | 09.08.22 | Safety Shoe | Pick from SSLLP
182110 | 11.08.22 | Spacers | Pick from SSLLP