## Vista
Prepared by: | vanajakshi
Report Date | 25.08.2022
Site | Greenwood Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142102 | 26.07.2022 | Armored cable | Duplicate sent to MD'S Approval
142117 | 02.08.2022 | MS &GI material | Po to be issue
142142 | 16.08.2022 | Electrical wires | PO No:91069
142148 | 17.08.2022 | GI nut with washer | Po to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
141357 | 6.04.2022 | MS Z angles | Pickup from SOV
141889 | 24.05.2022 | Sofa set 2+1 | Next week delivery
141922 | 30.05.2022 | Cafeteria +bar+Library cabinets | Next week delivery
141964 | 11.06.2022 | Floor tiles country almond | Pickup from GMR
142051 | 07.07.2022 | Large tiles (Tagus & marbo opera )tiles | Pickup from GMR
142052 | 07.07.2022 | Large tiles (regal beige) | Pickup from GMR
142061 | 11.07.2022 | False ceiling material | supplier arranging material
142075 | 15.07.2022 | Creche toys & books | Next week delivery
142087 | 20.07.2022 | Taugs & Marbo-opera tiles | Pickup from GMR
142107 | 30.07.2022 | CP sink cock | Next week delivery
142110 | 01.08.2022 | CC Hume pipe | supplier arranging material
142111 | 01.08.2022 | Cutting blade | Delivered
142115 | 02.08.2022 | Guard alert siren | supplier arranging material
142118 | 02.08.2022 | Paints | supplier arranging material
142121 | 03.08.2022 | Regal Beige &Urbanwood dark tiles | Pickup from GMR
142112 | 1.08.2022 | MS Grills | Pickup from SOV