## KNM
Prepared by: | Deepa
Report Date | 25.08.22
Site | MRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
Follow up with suppleir
95165 | 04.07.22 | MS Z angle | Delivered
95177 | 28.07.22 | Door Salwood | Deliverd
95180 | 01.08.22 | Delivery challan book | Promotions to follow up
95181 | 02.08.22 | Guard alert siren | Next weak will be deliverd
95182 | 04.08.22 | safety material | Delivered
95186 | 12.08.22 | Hollow bricks | Follow up with suppleir
95187 | 12.08.22 | Hollow bricks | Follow up with suppleir
95188 | 12.08.22 | Floor Tiles | pick up from GMR