## Vista
Prepared by: | Ramya
Report Date | 2022-02-09
Site | SOV-part -3
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
184483 | 2022-06-08 | PVC coated GI wire | local purchase by site
184498 | 16-08-22 | UPVC Sliding mesh | po to be issue
184537 | 23-08-22 | plumbing PVC material | Po issued-Po no-91437
184538 | 23-08-22 | plumbing PVC material | Po issued-Po no-91438
184539 | 23-08-22 | plumbing PVC material | Po issued-Po no-91435
List of requisitions Where PO/WO is prepared and items have not received at site
184324 | 30-06-22 | Led gate light | pick up from SSLLP
184372 | 28-07-22 | Ultra Sprinkle HL, luna DK | pick up from GMR
184404 | 15-07-22 | Ultra Sprinkle HL, luna DK | pick up from GMR
184405 | 15-07-22 | ultra Sprinkle HL, luna DK & HL | pick up from GMR
184406 | 15-07-22 | Wall & floor tiles | pick up from GMR
184410 | 18-07-22 | malaysian brown DK & HL | pick up from GMR
184420 | 19-07-22 | printer cable | local purchase dy site
184461 | 29-07-22 | wall hung EWC with seat cover | pick up from SSLLP
184463 | 2022-01-08 | Crack fill chemical | Follow up with supplier
184474 | 2022-03-08 | wall plug fisher 5 mm & white cement | pick up from SSLLP
184480 | 2022-05-08 | plumbing Sanitary | pick up from SSLLP
184485 | 2022-08-08 | ultra Sprinkle HL, malaysian brown DK & HL | pick up from GMR
184489 | 2022-10-08 | Electrical copper wire | pick up from SSLLP
184494 | 20-08-22 | country chocolet & crema marfil | pick up from GMR
184495 | 20-08-22 | ceramic tiles luna DK & HL &LT Ultra sprinkle | pick up from GMR
184507 | 17-08-22 | CP Sink cock with swivel spout | pick up from GMR
184509 | 17-08-22 | Electrical conducting material | pick up from SSLLP
184510 | 17-08-22 | Electrical conducting material | pick up from SSLLP
184511 | 17-08-22 | Electrical conducting material | pick up from SSLLP
184512 | 17-08-22 | Electrical conducting material | pick up from SSLLP
184513 | 17-08-22 | Electrical conducting material | pick up from SSLLP
184514 | 17-08-22 | Electrical conducting material | pick up from SSLLP
184515 | 17-08-22 | Hold fast | pick up from SSLLP
184517 | 18-08-22 | CP shower arm 3nos & CP short body | pick up from SSLLP
184522 | 19-08-22 | Vertified tiles | deliverd
184523 | 22-08-22 | CPVC material & water tank | pick up from SSLLP
184524 | 22-08-22 | CPVC material & water tank | pick up from SSLLP
184525 | 22-08-22 | CPVC material & water tank | pick up from SSLLP
184528 | 22-08-22 | Panel doors | pick up from SSLLP
184532 | 22-08-22 | Electrical swich 6 amps | pick up from SSLLP
184534 | 22-08-22 | CPVC Reducer FTA | pick up from SSLLP
184535 | 23-08-22 | Test apparatus slump cone | pick up from SSLLP
184536 | 23-08-22 | SS Screws half thread | Follow up with supplier
184540 | 23-08-22 | Doors internal beading | deliverd
184545 | 24-08-22 | Electrical wires | pick up from SSLLP
184546 | 23-08-22 | CP Plumbing material | pick up from SSLLP
184547 | 23-08-22 | sanitary material | pick up from SSLLP