## NE
Prepared by: | Ramya
Report Date | 02.09.22
Site | Serene Farms
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
175325 | 20-07-2021 | solar module | Legal case is going on supplier
175492 | 2022-07-03 | Sliding windows | fallow up with supplier
175513 | 23-06-2022 | furniture | fallow up with supplier
175515 | 2022-07-07 | Sliding window with mesh | fallow up with supplier
175517 | 15-07-2022 | Floor tiles | pick up from GMR
175525 | 19-08-22 | MS Grills | fallow up with Purushotham sir