## MPPL
Prepared by: | Mounika
Report Date | 2022-08-27
Site | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178723 | 19.08.22 | UPVC French Door | Estimation sent to MD Approval
178720 | 16.08.22 | PVC False ceiling | Estimation sent to MD Approval
List of requisitions Where PO/WO is prepared and items have not received at site
178127 | 29.01.21 | Wall Hung | Bulk Order
178477 | 31.03.22 | Touhened Glass | Pick from SSLLP
178479 | 05.04.22 | Grills | Pick from SSLLP
178551 | 06.05.22 | Tiles dark wood | Pick from GMR
178558 | 14.07.22 | Wires | Pick from SSLLP
178578 | 31.05.22 | Panel Doors | Pick from SSLLP
178617 | 24.06.22 | Malasin Tiles | Pick from GMR
178620 | 27.06.22 | Timer & L & T | Pick from Supplier
178647 | 13.07.22 | Tan Brown Granite | Pick from SSLLP
178653 | 16.07.22 | Book Collection | Pick from Supplier
178661 | 19.07.22 | Tan Brown Granite | Pick from SSLLP
178660 | 19.07.22 | CC TV Camera | Pick from SSLLP
178666 | 20.07.22 | Spring Wire | Pick from Supplier
178670 | 22.07.22 | Timer | Pick from Supplier
178679 | 30.07.22 | Ranger Blue | Pick from GMR
178689 | 02.08.22 | Guard Alert | Pick from Supplier
178690 | 02.08.22 | CC TV Camera | Pick from SSLLP
178693 | 02.08.22 | Glass Mosaic Tiles | Pick from Supplier
178694 | 02.08.22 | Garden Rake | Delivered
178703 | 08.08.22 | Exhaust Fan | Pick from Supplier
178706 | 09.08.22 | MS Grills | Pick from SSLLP
178708 | 09.08.22 | Kitchen Cabinate | Work Under Process
178712 | 10.08.22 | False ceiling lights | Pick from SSLLP
178717 | 13.08.22 | Country rosso | Pick from GMR
178722 | 19.08.22 | Chimney-Hindware | Pick from Supplier
178726 | 20.08.22 | Acid | Pick from SSLLP