## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-09-03
Site |  | GMR
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Missing requisitions
193694 |  | Missing requisition | No attachment found with email, kindly send it again.
List of requisitions Where PO/WO not prepared 3 working days after requisition:
193717 | 2022-08-24 | Glass balcony railing | PO 91522
193728 | 2022-08-24 | UPVC Windows | PO 91523
193739 | 2022-08-29 | MS Material | PO 91709, 91705, 91712
193741 | 2022-08-29 | Round bombay nails, chain | Local purchase by Selva, follow up with him
193744 | 2022-08-30 | Hardware material | PO 91639
193745 | 2022-08-30 | CPVC Material | PO 91578
193746 | 2022-08-30 | CPVC Material | PO 91593
193747 | 2022-08-30 | PVC Material | PO 91595
193748 | 2022-08-30 | PVC Material | PO 91597
193749 | 2022-08-30 | Hardware material | PO 91624, 91629, 91632
193755 | 2022-08-30 | Lift material | Cancelled due to qty not mentioned in the requisition
193756 | 2022-08-30 | Lift material | Cancelled due to qty not mentioned in the requisition
193757 | 2022-08-30 | Electrical and CPVC material | PO 91582
193762 | 2022-08-30 | Plumbing material | PO 91580
193692 | 2022-08-19 | Panel doors and Beeding | PO 91194
193755 | 2022-08-30 | Lift material | G,C Block estimate with MD for approval
List of requisitions Where PO/WO is prepared and items have not received at site
193159 | 2022-05-05 | Tan brown granite | Deliverd
193300 | 2022-06-07 | Glass balcony railing | Work under process, com ordinate with supplier
19336 | 2022-06-22 | Tan brown granite | Deliverd
193398 | 2022-06-29 | False ceiling work | Work under process, co-ordinate with supplier
193399 | 2022-06-29 | False ceiling work | Work under process, co-ordinate with supplier
193406 | 2022-06-30 | Glass balcony railing | Work under process, co-ordinate with supplier
193407 | 2022-06-30 | False ceiling work | Work under process, co-ordinate with supplier
193454 | 2022-07-12 | UPVC Ventilator | Under fabrication
193461 | 2022-07-12 | Short body | Today we are receiving the stock from supplier, will issue by tomorrow from SSLLP
193467 | 2022-07-13 | Plumbing material | PO to be issue
193469 | 2022-07-13 | Tan brown granite | Work under process, co-ordinate with supplier
193504 | 2022-07-21 | MS Grills | work under process
193505 | 2022-07-21 | MS Grills | work under process
193529 | 2022-07-27 | MS Round pipe b-class | Deliverd
193568 | 2022-08-03 | Short body, shower arm, sink cock | Today we are receiving the stock from supplier, will issue by tomorrow from SSLLP
193569 | 2022-08-03 | Rack bolts wash basin | Today we are receiving the stock from supplier, will issue by tomorrow from SSLLP
193594 | 2022-08-06 | Plumbing material | Pick up from SSLLP
193596 | 2022-08-06 | Plumbing material | Pick up from SSLLP
193597 | 2022-08-06 | MS Reducer, MS Elbow | Pick up from Global
193604 | 2022-08-08 | CPVC Elbow 20 mm | Deliverd
193606 | 2022-08-08 | Hardware material | Pick up from SFS hardware
193607 | 2022-08-08 | Electrical wires | Pick up from SSLLP
193608 | 2022-08-03 | Cat 6 cable-D link | Deliverd
193616 | 2022-08-10 | Glass balcony railing | Work under process
193618 | 2022-08-10 | Short body | Today we are receiving the stock from supplier, will issue by tomorrow from SSLLP
193621 | 2022-08-10 | Panel doors and hardware material | Pick up from ssllp, tomorrow
193624 | 2022-08-11 | MS Round pipe b-class | Deliverd
193639 | 2022-08-12 | Cement fiber board | Work under process
193644 | 2022-08-13 | CP Material | Today we are receiving the stock from supplier, will issue by tomorrow from SSLLP
193645 | 2022-08-13 | Shower arm, health faucet | Today we are receiving the stock from supplier, will issue by tomorrow from SSLLP
193647 | 2022-08-16 | GI U clamp+Nut | PO to be issue
193649 | 2022-08-16 | PVC Rigid pipe, PVC plain bend, GI U clamp | Pick up from SSLLP
193654 | 2022-08-16 | CPVC Material | Pick up from SSLLP
193660 | 2022-08-16 | Short body, sink cock with swivel spout | Today we are receiving the stock from supplier, will issue by tomorrow from SSLLP
193666 | 2022-08-17 | CP Material | Today we are receiving the stock from supplier, will issue by tomorrow from SSLLP
193667 | 2022-08-17 | Wall hung rubber washer parryware | PO to be issue
193671 | 2022-08-17 | Tan brown granite | Pick up from SOVLLP
193672 | 2022-08-18 | PVC Single Y, PVC Door bend | Pick up from SSLLP
193674 | 2022-08-18 | CPVC Elbow, coupling reducer tee | Pick up from SSLLP
193676 | 2022-08-18 | Hardware material | Pick up from SFS hardware
193679 | 2022-08-18 | Furniture &Fixtures kitchen cabinets | Follow up with KBD
193682 | 2022-08-19 | Plants grass koren | Follow up with Radhakrishna
193688 | 2022-08-19 | Electricals wires | Deliverd
193690 | 2022-08-19 | CP Material | Today we are receiving the stock from supplier, will issue by tomorrow from SSLLP
193691 | 2022-08-19 | CP Material | Today we are receiving the stock from supplier, will issue by tomorrow from SSLLP
193699 | 2022-08-20 | CPVC Material | Pick up from SSLLP
193750 | 2022-08-30 | Plumbing material | Deliverd
193711 | 2022-08-23 | CP Material | Today we are receiving the stock from supplier, will issue by tomorrow from SSLLP
193712 | 2022-08-23 | Plumbing material | Today we are receiving the stock from supplier, will issue by tomorrow from SSLLP
193718 | 2022-08-24 | Electrical wires | Today we are receiving the stock from supplier, will issue by tomorrow from SSLLP
193719 | 2022-08-24 | Plumbing material | Pick up from SSLLP
193720 | 2022-08-24 | Plumbing material | Pick up from SSLLP
193721 | 2022-08-24 | CPVC Material | Pick up from SSLLP
193723 | 2022-08-24 | CPVC Material | Pick up from SSLLP
193723 | 2022-08-24 | Hardware material | Pick up from Supplier
193724 | 2022-08-24 | Plumbing &hardware material | Pick up from SSLLP
193730 | 2022-08-24 | Hardware material | Pick up from SFS hardware
193735 | 2022-08-27 | Plumbing material | Pick up from SSLLP
193738 | 2022-08-29 | Tools FRP Thadkas | Followup with Meera fibertek
193740 | 2022-08-29 | MS Square pipe | Deliverd
193742 | 2022-08-29 | MS Round pipe b-class | Follow up with Dilpreet tubes for delivery
193752 | 2022-08-30 | CP Material | Today we are receiving the stock from supplier, will issue by tomorrow from SSLLP
193754 | 2022-08-30 | CP Material | Today we are receiving the stock from supplier, will issue by tomorrow from SSLLP
193758 | 2022-09-01 | Electrical material | Pick up from SSLLP