## Vista
Prepared by: | vanajakshi
Report Date | 08.09.2022
Site | Greenwood Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142102 | 26.07.2022 | Armored cable | Duplicate sent to MD'S Approval
142137 | 9.08.2022 | cable tray | Rates Under Negosiation
List of requisitions Where PO/WO is prepared and items have not received at site
141357 | 6.04.2022 | MS Z angles | Pickup from SOV
141964 | 11.06.2022 | Floor tiles country almond | Pickup from GMR
142051 | 07.07.2022 | Large tiles (Tagus & marbo opera )tiles | supplier arranging material
142052 | 07.07.2022 | Large tiles (regal beige) | supplier arranging material
142075 | 15.07.2022 | Creche toys & books | Next week delivery
142087 | 20.07.2022 | Taugs & Marbo-opera tiles | Pickup from GMR
142115 | 02.08.2022 | Guard alert siren | supplier arranging material
142117 | 02.08.2022 | MS & GI Material | Delivered
142121 | 03.08.2022 | Regal Beige &Urbanwood dark tiles | Pickup from GMR
142148 | 17.08.2022 | GI threaded Rod with nut | supplier arranging material
142152 | 18.08.2022 | Toys-cars &dolls | Next week delivery
142158 | 22.08.2022 | GI Plumbing | Delivered
142159 | 23.08.2022 | SS Dust bin | supplier arranging material
142163 | 24.08.2022 | MS mesh work | supplier arranging material
142135 | 24.08.2022 | GI threaded rod with nut | supplier arranging material