## KNM
Prepared by: | sneha
Report Date | 08.09.2022
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
165719 | 30.08.22 | Eco drain pipe | po issue 91753
165720 | 03.09.22 | white cement | po issue 91603
165721 | 03.09.22 | stationary | po issue 91613
List of requisitions Where PO/WO is prepared and items have not received at site
165643 | 07.5.22 | Timer Machines | Next weak delivey
165645 | 09.05.22 | Ms gate-v.no.16 | Next weak delivey
165646 | 09.05.22 | Ms gate-v.no.18 | Next weak delivey
165664 | 26.05.22 | Garbage Bin | Next weak delivey
165688 | 06.07.22 | MS Grill | Next weak delivey
165701 | 02.08.22 | Guard siren | Next weak delivey
165708 | 20.08.22 | Shower arm | Pick up from Ssllp
165710 | 22.08.22 | cp items | Pick up from Ssllp
165712 | 22.08.22 | cp items | Pick up from Ssllp
165713 | 22.08.22 | Waste pipe | Pick up from Ssllp
165714 | 22.08.22 | cp items | Pick up from Ssllp
165718 | 27.08.22 | panel door | Pick up from Ssllp